|  | Journal of Information Systems The journal of the Information Systems Section of the American Accounting Association |
| --- | --- |

The Information Systems Section

Midyear Meetings:

An Overview and Timeline

Acknowledgement:  This manual is adapted from the Management Accounting Section’s Midyear Meeting Manual, with their permission.  We thank MAS for sharing their manual with the IS section.

Version 3.0

May 20, 2006

TABLE OF CONTENTS

Overview

## Regular Meeting Planning Committee

## AIS New Scholar Consortium

## JIS Workshop

## CPE Sessions

Timeline: Tasks and Deadlines

Notes to the Timeline

Note 1.  	Co-locating the conference with other AAA section meetings

# Note 2.  	Date and location choices

Note 3.  	Preparing information for the hotel bid

Note 4.  	Choosing from among the hotel bids

# Note 5.  	Selecting and communicating with speakers

Note 6.  	The Call for Papers/Announcement of Meeting

Note 7.   	Evaluating paper submissions

Note 8.   	Obtaining sponsors

Note 9.  	The Registration Form and fees

Note 10. 	Forming the Program

Note 11. 	Making papers available online prior to the Meeting

Note 12. 	Categorizing Sessions for CPE credit

Note 13. 	Post Program on the Web

Note 14. 	Final hotel details

Appendices:  Related Documents

- Planning Document

- Initial Bidding Document

- Call for Papers - Regular Conference

- Call for Papers - New Scholar Consortium

- Meeting Announcement

- Hotel Information

- Participant Registration Form

- Letter to Reviewers

- Reviewer Evaluation Form

- Conference Rejection Letter

- Conference Acceptance Letter

- Forum Acceptance Letter

- Author/Discussant Guidelines for Research Papers

- Moderator Guidelines

- Volunteer Form (2006 – online only)

- Final Report to the Section

- Midyear Meeting Budget

- Final Program

- Conference Evaluation Form

Prior Year Programs

- 2006, 6th Annual AAA-IS Midyear Meeting - Savannah

- 2006, 5th Annual AAA-IS Midyear Meeting – Scottsdale

- 2005, 4th Annual AAA-IS Midyear Meeting – New Orleans

- 2004, 3rd Annual AAA-IS Midyear Meeting – Clearwater

- 2003, 2nd Annual AAA-IS Midyear Meeting – San Diego

- 2002, 1st Annual AAA-IS Midyear Meeting – Orlando

OVERVIEW

# The AAA-Information Systems Section's midyear conference requires significant long-range planning.  This manual is to help those responsible for this effort and should be handed down to successive Program Chairs.  During August-September, two Program Chairs are working on their meetings:  the Program Chair for the upcoming meeting (Program Chair 1), and the Program Chair for the meeting after that (Program Chair 2).  That’s because Program Chairs are usually selected 18 months out.  The manual can be used simultaneously, but Program Chair 1 should be the only one to make changes to the manual.  After that meeting is over, Program Chair 1 can make any final edits to the manual and send it to Program Chair 2.

# The IS Section midyear meeting is actually three different meetings linked together: the AIS New Scholar Consortium (formerly known as our doctoral consortium) which meets the first day, The JIS Research Workshop, which meets the afternoon of the New Scholar Consortium on the first day, and the regular midyear meeting conference that meets the second and third days.

## Regular Meeting Planning Committee

## The IS bylaws identify the following positions as the midyear meeting planning committee:

## Program Chair

## JIS Editor

## Conference-Only paper coordinator

## Education paper coordinator

## IS Section president (advisory capacity)

## AIS New Scholar Consortium Coordinator

## JIS Workshop Coordinator

## The Program Chair is appointed 18 months in advance of the meeting by the IS President and President-Elect.  The program chair coordinates with other members of the planning committee to ensure a timely planning process and effective meeting.  The program chair must:

## choose the site and date (in conjunction with the planning committee)

## complete the initial bidding document and send to Dee Strahan, the AAA meeting coordinator (check with the AIS New Scholar Consortium Coordinator and the JIS Workshop Coordinator to ensure that their space requirements are included in the bid)

## coordinate with other planning groups

## conduct planning meeting at midyear meeting (one year in advance of meeting)

## conduct planning meeting at AAA annual meeting (5 months in advance of meeting)

## work with the AAA meeting coordinator to contract with the hotel

## choose and recruit the plenary and luncheon speakers

## publicize the conference

## issue call for papers

## solicit discussants and moderators

## schedule number of sessions and types

## select menus (in conjunction with the AAA meeting coordinator)

## work up and monitor the budget

## arrange for conference and forum papers to be posted on the IS Section Web site

## send out blast emails periodically as needed (send to the IS President who sends to AAA for distribution)

## draft the program

## post moderator, discussant, and author guidelines on the section web site

## work with AAA staff to have table-top tent cards, name badges, and registration packets assembled (and any other printing requirements)

## work with AAA staff to have Best Paper Award plaques made for presentation at the Meeting

## work with AAA meeting planner to determine AV needs and costs

## coordinate with the Technology Manager   (NOTE: as of the 2006 Meeting, three Section members are solicited to bring a laptop and compatible portable projector for use in the concurrent paper sessions.  Two will be used, the third is for back-up purposes. The Technology Manger is responsible for identifying these volunteers and is the custodian of the Kensington locks to protect the equipment.)

## oversee the conduct of the meeting

## handle anything unexpected that shows up during the meeting

## coordinate with the Section Historian to be sure plenty of pictures are taken at the Meeting and displayed on the Web site shortly after the Meeting

## Double check with the AAA staff to ensure that appropriate items are included in the registration packet.  Examples of items to include in registration packet include:

## Program with room assignments

## Meal tickets

## List of participants

## CPE form

## AIS New Scholar Consortium

## The AIS New Scholar Consortium is open to doctoral students and 1st and 2nd year AIS assistant professors.  The New Scholar Consortium provides guidance on effective teaching of AIS, and research issues and opportunities in AIS.  In recognition of the unique challenges of teaching and conducting research in the AIS area, the IS section opened the consortium to 1st and 2nd year AIS assistant professors at the 2004 meeting.

## Funding for the consortium of $5,000 per year is provided by the KPMG Foundation. Bernie Milano (bmilano@kpmg.com) through Stephanie Bryant is our contact with the Foundation.  The funding is pledged for 3 years, starting in 2004.  We must renew the request with the Foundation prior to the end of the third year (e.g., prior to the 2006 meeting).  This funding allows the Section to waive the normal registration fee for doctoral students.  We limit the waiver to doctoral students who are members of the IS section.  The registration fee is not waived for first and second year assistant professors who participate in the consortium. The IS section does not cover any room costs for doctoral students.

## The consortium begins with a reception the night before, followed by a full day the next day.  The afternoon of the consortium has typically been a workshop – in previous years we had the JIS Workshop, in 2007 we had an Education workshop.  Generally, a separate person coordinates the JIS workshop part of the consortium.

## The AIS New Scholar Consortium Coordinator is appointed 18 months in advance of the meeting by the President and President-Elect of the IS Section.  This individual’s main responsibilities are to:

## plan the consortium

## recruit session leaders

## recruit participants (both doctoral students and new AIS profs)

## publicize the consortium through blast emails

## oversee the conduct of the consortium (except for the JIS Workshop)

## handle anything unexpected for the consortium portion of the meetings

## send Thank You notes to session leaders

## JIS Workshop

## The purpose of the workshop is to improve the research skills of Accounting Information Systems PhD students and faculty.  Members of the Journal of Information Systems Editorial Board critique accepted workshop participants’ papers.  In addition, accepted workshop participants receive two papers to review and critique.  At the workshop, participants meet in small groups to discuss their work with the critiquing editorial board member and workshop participants.  The goal of this interaction is to develop submitted work for future journal submission. Accepted workshop participants are not obligated to submit completed works to JIS.

## Selection for the JIS Research Development Workshop is competitive.  Submitted papers: (a) should address issues related to information systems and (b) must not be currently submitted for publication at a journal.  Papers concurrently submitted to or scheduled for presentation at conferences are welcome.  Participation in the workshop is restricted to AAA-IS section members.  Priority will be given to submissions from the following (in order of priority): Ph.D. students, untenured faculty, and researchers from outside the USA.

## The JIS Workshop Coordinator is appointed 18 months in advance of the meeting by the President and President-Elect of the IS Section.  This individual’s main responsibilities are to:

## plan the workshop

## coordinate with the Program Chair and the AIS New Scholar Consortium Coordinator

## solicit members of the JIS editorial board to participate

## recruit doctoral students and 1st and 2nd year assistant professors

## recruit speakers

## oversee the conduct of the workshop

## handle anything unexpected for the consortium portion of the meeting

## send Thank You notes to the editorial board participants

## CPE Sessions

## The first year we held any CPE sessions at the midyear meeting was in 2004. The only CPE offered in the past was SMAP (Semantic Modeling of Accounting Phenomena), which was conducted by Julie Smith David and Bill McCarthy.  For 2004, we charged $60 for a full day session, but this does not cover the meal and overhead (room and AV) costs for the session.

## In 2006, we changed the fee to $120 for a full-day session.  This includes the cost of meals, room, and t-shirts.  Julie Smith David will bring her own laptop and projector, so that the only cost for AV is a screen to view the slides.

## In the future, we might choose to offer additional CPE sessions.  We can offer any sessions that are of interest to the Section. If the session doesn’t make, it can be cancelled. However, the decision usually needs to be made as far in advance as possible so that the AAA Meeting Coordinator can arrange for rooms to accommodate these sessions.

## In 2007, we offered a free AIS Education Workshop on Wednesday afternoon, after the New Scholar’s Consortium let out, and opposite the afternoon SMAP session.

TIMELINE

DATE			ACTION

August 		New conference organizers selected

(18 months prior)	All organizers read this manual

Executive committee considers whether joint meeting is desired

If joint meeting is desired, Program Chair immediately contacts other AAA sections to see if possible – Note 1

September 		If co-location is not possible,

(16 months prior)	Make a list of desired dates and cities – Note 2

Prepare initial bidding document – Note 3

Send bidding document to AAA Meeting Coordinator (Dee Strahan)

Mid-November	Receive hotel bids and report from AAA Meeting Coordinator – Note 4

(14 months prior)	Program Chair makes recommendation to planning committee for location

Mid-December	Negotiations with hotel completed; location for conference decided

(13 months prior)

January 		Go to IS meeting prior to yours

(12 months prior)	Announce dates, location of next year’s conference at lunch or other venue

Have Call for Papers for your meeting at registration desk – Note 5

Meet with current year’s program chair and planning committee at the

current year meeting

February		Decide on and contact Plenary speakers – Note 6

(11 months prior)

March			Advertise the meeting

Post AIS New Scholar Consortium Call for Papers, Midyear Meeting Call 
     for Papers, Meeting Announcement, hotel information on IS section 
     web site

Inform AAA Web master of the posted information and they will link to

our site.

Work up the BUDGET for the Meeting

June			Make a list of persons who actively publish research - contact them to 
                             encourage them to submit/discuss papers

Send blast e-mail to IS section about the conference

Send AAA and IS Section Web Master the hotel and registration

information so that online registration can be set up – AAA also needs

preliminary program outline – Note 7

3rd week in July	Send blast e-mail to IS section reminding them of submission deadline   
     (September 15th)

Determine whether SMAP (and any other CPE) will be offered

AAA Annual 		Provide a status report to the IS business meeting

Meeting		Purchase tickets/make hotel reservation for yourself for January

Contact Sponsors – Note 8

Ask the AAA staff for the prior year's actual budget numbers

Work out any details regarding timelines for paper submissions with the
                                   JIS Editor and the Conference-Only paper coordinator

Decide timeline for Best Paper Awards decision so that plaques can be 
     made by the AAA in time to present them at the Midyear Meeting

September 15	Deadline for paper submissions

September 19	All papers must be sent to reviewers (responsibility of JIS Editor and the Conference-Only paper coordinator) – Note 9

September 30		All moderators assigned to sessions

Contact New Scholar and JIS Workshop Coordinators for update

Format Rules for JIS and for Concurrent Paper Sessions posted on website

Prepare preliminary Program – Note 10

October 14		All reviews completed; JIS Editor and the Conference-Only paper 
                 coordinator should have conference call immediately to assign papers 
                 to sessions

Coordinate with IS Section web master to post Final Program, as well as

papers for concurrent sessions and forum session

Blast E-mail reminding people of the early registration and hotel deadlines

November 8		Research and Publications Committee Chair (research papers) and the

Education Issues Committee Chair (educational papers) advise the

Program Chair of the papers/authors who are selected for the Best

Paper Awards (Note 11)

November 11		Final draft of all sessions to Program Chair (send final draft to President 
                 and Coordinators for the New Scholar Consortium as a final review)

Program Chair sends final draft of Program to AAA for printing 
     (registration packages for Meeting)

Inform AAA of Best Paper Award winners so that plaques can be made

Inform AAA of any individuals who will receive “Complimentary” 
                  registration (e.g., Plenary Speaker and any others as determined by the 
 	      President and Program Chair)

Inform AAA that no hotel rooms are complimentary

Remember to order “tent cards” (through AAA) for all participants in  
                  Consortium and JIS Workshop, as well as any panelists during the 
                  regular Meeting

Inform AAA of any sponsorship (e.g., KPMG) for signage and details for 
                  invoicing sponsor for event (New Scholars Consortium)

Contact AAA (Linda Watterworth), to determine how each session at the Meeting will be categorized for CPE credit. This is required for the CPE

form that is included in the registration packet – Note 12

Post Program on the Web, and as many papers as possible – Note 13

December 2		Final versions of papers (only those accepted by JIS) posted to web site

Determine gift for Plenary Speaker.

December 5	            Final Hotel Details – Note 14

Work with AAA meeting planner on menus

Work with AAA meeting planner on AV needs

Finalize budget

Make sure plenary speaker is coming, and determine a suitable Speaker

Gift to present upon completion of the Plenary Address

Two Weeks Prior

to Meeting:	Call the President of the Section and have a teleconference to go through 
the Program, item-by-item for each day to be sure each person knows what they are to do and as a last-minute check of all details regarding the Meeting. Prepare a checklist of last minute details to attend to if necessary.

IS conference		Follow through with schedule

Deal with program emergencies

Meet with next year's organizers

Give update to IS Executive Committee

Make any final updates to Manual and pass to next year’s Program Chair

NOTES TO THE TIMELINE

Note 1. Co-locating the conference with other AAA section meetings

One intriguing possibility is to hold the IS conference on the same dates/in the same hotel as one of the other midyear section meetings.  The idea is that having two midyear meetings in the same spot increases the choices available to everyone as well as cuts down on the travel costs for those persons who would have gone to both midyear meetings anyway.  The conferences would each continue to have their own structure, but people could cross-attend sessions.  Additionally, some sessions could be cross-listed and some sessions mixed. The prime candidates for a co-located conference is either the Auditing Section or the Management Accounting Section.

In 2003 we co-located with the Management Accounting Section at the San Diego meeting.  The meeting was well-attended and people seemed to like the joint meeting idea. The Executive Committee seemed to favor perhaps every other year or every third year for a joint meeting.  A proposal to co-locate a meeting should go before the IS Executive Committee for discussion and final decision.

There are several hurdles to overcome to make a joint meeting happen.  First, you need to move quickly.  The midyear meeting locations for the other sections are typically decided by one person who makes the date, location, and hotel choices. Unless you contact that person(s) immediately, they will be locked into choices that preclude co-location.  Second, the MAS midyear meeting is approximately three times the size of the other midyear meetings, so a co-located conference needs a fairly large hotel. This may restrict choices.

If it looks like a co-located conference is feasible, you will need to select the dates, etc… fairly quickly.  Information about these choices is given in Note 2.

# Note 2.  Date and Location Choices

As of the 2004 conference, the conference takes place over three days.  Thursday is the doctoral consortium, and the regular meeting is held on Friday and Saturday.

The meetings are usually held the first weekend in January.  The choice of location has very few constraints.  You need to come up with three different potential cities in which to hold the conference.  A warm place with interesting activities/nightlife is always a winner.  You could break with tradition and try a spot within easy travel distance of skiing, such as Albuquerque or Denver.  You should try to avoid: the location of the last 2-3 AAA meetings, the location of any of the other mid-year meetings (particularly auditing), and the last 2-3 places where the MAS section has been held.

Other things to think about in choosing a location.  An airport hub is usually preferred, since it involves fewer connecting flights for travelers.  Also, try to select a location in the 48 states.  Hawaii and Alaska are too far for most people.  Holding the conference outside the US (i.e. Canada, Puerto Rico) leads to too many visa problems.  Additionally, many schools will not fund international travel.

Once you decide on a date and three potential locations, you need to coordinate with the President and President-Elect of the Section.  Next, generate a fairly detailed conference schedule that will serve as the initial bidding document.  This process is described in Note 3.

Note 3.   Preparing the information for the hotel bid

To obtain hotel bids for your conference, Dee Strahan, the AAA Meeting Coordinator needs to know the approximate number of people who will attend as well as the number/size of rooms needed throughout the conference. The best way to do this is to start with the previous year’s room allocation and make whatever changes are necessary.

The New Scholar’s space allocation needs to be cleared with their coordinator.  Similarly, the JIS Workshop coordinator needs to sign off on their space allocation.

Papers that are not accepted for the regular meeting are usually accepted for the forum.  The forum takes place on Saturday morning and works well if it’s done in conjunction with breakfast.  The forum is not a formal presentation of papers.  Rather, authors are stationed at tables with tent cards and interested people approach them to discuss their papers.

Once you have the space allocation set, you send it to the AAA conference staff.  They will send the conference out for competitive bidding.  It takes about six – eight weeks for the hotels to respond and the AAA staff to send you a report.  As soon as you receive this report, send e-copies to the President and President-Elect for a discussion and decision of location.

Note 4.  Choosing from among the Hotel Bids

In our experience, the AAA staff report is professionally done and identifies great choices.   You need to pick one city and your first choice hotel (and also a backup hotel).  Be careful!  Some hotels may offer extra large rooms to conference organizers, provide extra meals, etc.   These perks usually mean significantly higher rates for conference attendees.

Select the hotels as quickly as possible.  The fact that the hotel has bid does not lock them into the conference.  Hotels bid on many conferences and you may not get your first choice if you take too long to decide.  Once the AAA Meeting Coordinator knows which hotel(s) to concentrate on, she will begin the negotiations over the contract.  This process can take anywhere from two weeks to two months.

A good target to shoot for is to be able to announce the dates and location at the IS meeting the year before yours.  You may/may not know the hotel by then, but can let people know the dates/locations.  Announcing the next meeting's dates and location provides a sense of continuity to the section members.  It reinforces the idea that the section meetings are an on-going activity they should plan for.

Note 5.  The Call for Papers/Advertising the Conference

Advertising the conference is key to getting a large turnout.  You will need to write a call for papers that provides information about how to submit papers to both the regular meeting and the New Scholar Consortium.

The IS section has a special relationship with our section journal, the Journal of Information Systems.  While we The Section allows a person to simultaneously submit a paper to the IS conference and JIS.  The editor of JIS agreed to have the papers processed within our timeline as well as waive the submission fee.  This is excellent advertising for our section journal.  You will need to work with the editor well in advance to set this up.

The Call for Papers needs to be sent both to the AAA newsletter and the IS newsletter.  Also, have the IS webmaster put the call on the IS website, and include a link to the AAA website.

It is an excellent idea to send a blast e-mail to all IS section members one week before the paper submission deadline.  Many people will have forgotten or not noticed the approach of the deadline and a reminder helps.

# Note 6.  Selecting Speakers

There is usually one plenary speaker at the conference.   This has historically been the incoming AAA president-elect who serves as the “kickoff” speaker.  His/her talk is attended by the entire conference.  It is a good idea to have the speaker with the greatest visibility start off the conference.  We usually have them discuss their vision for the IS section and how it fits into AAA’s overall strategic plan.  However, the Program Chair and planning committee can allow a different topic at their discretion.

Other speakers might be selected for the Friday and/or Saturday lunches.  These speakers could be either from academia or practice.  We usually like to invite the JIS Editor to announce the Best Paper Awards at one of the lunches and keep the other one as open time for attendees to network with their colleagues.  Speakers set the tone of the conference and getting good speakers is difficult.  The major players in both academia and business set their schedules months, if not years, in advance.  Try and contact them/line them up as soon as you know the dates/location of the conference.

As a small inducement, the conference fee is “Complimentary” for the plenary speaker.  On the registration form the speaker should put down something like "My registration fee has been waived by the program chair.  Please contact them if you have any questions."  The Section also pays for the hotel room for the plenary session speaker and any other invited speaker outside the Section.  However, it is important for the speaker to know that he/she must make any room reservations and will be reimbursed by the Treasurer of the Section.

Below is a sample of the information that was sent to the 2006 Plenary Speaker:

September 4, 2005

Dear Professor Sunder:

It’s a little early, but I have some information regarding our IS Section Mid-Year Meeting that I wanted to send to you.  First, our Plenary Session is scheduled for 8:30 – 10:00 AM on Friday morning, January 6, 2006.  I will take about 15 minutes to welcome everyone, acknowledge workers, and then introduce you.  We received $5,000 from KPMG in support of our New Scholar Consortium, so I’m hoping that Bernie Milano will attend and offer a few comments regarding their Foundation.  I think it would be great if you could plan to speak for about an hour and the remaining few minutes could be used for Q&A’s with the audience.

Second, of course our Section will reimburse you for the cost of the hotel, but you will need to make your own reservation.  After the meeting, please send your request for reimbursement to Vernon Richardson, our Treasurer for the IS Section. His contact information is as follows:

Vernon J. Richardson
University of Kansas Business School
350F Summerfield Hall
Lawrence, KS 66045
Phone:  (785) 864-7507
Fax: 785-864-5328
Email:  vrichardson@ku.edu

Our Meeting is at the Doubletree Paradise Valley Resort in Scottsdale, AZ.  The toll-free reservations number is: 1-877-445-6677, and their website is:  www.paradisevalley.doubletree.com.  If you would like some hotel information, here is the link:  http://aaahq.org/infosys/conferences/hotel_info.htm

Note 7.  The Registration Form and the Registration Fee

The conference fee has been in the neighborhood of $200.  This fee was changed to $225 for the 2006 Meeting in an attempt to come closer to breaking even for the Conference.  In addition, we now charge Ph.D. students $10 so that they may register online.  This “complimentary” registration for Ph.D. students is ONLY offered to those students who are already members of the AAA and members of the IS Section.  All other Ph.D. students must pay the full registration is they wish to attend the conference or the SMAP training.  The only exception is international students since the AAA has no provision for these students to be members. They may be charged only the $10 fee and may register online.

If any professors are not members of the AAA or are not members of the IS Section, they may attend SMAP training but must still pay the full registration fee.  For the 2006 Meeting, a computer information systems (CIS) professor and a CIS Ph.D. student wanted to attend SMAP and were allowed to do so although neither were members of the AAA and they were not interested in attending the Section Meeting.  However, they were each required to pay the full registration fee for the conference.

We actually do not break even on the conference, even with the KPMG funding.  The Appendix provides a budget you can use to help plan the conference costs.  It includes a CVP analysis that will guide you as to the cost you should charge to break even.  However, the Section usually opts to subsidize part of the cost of the meeting rather than increase the registration fee to break even.

Your starting point for the budget is last year’s numbers. Be forewarned that it is difficult to get the prior year's conference data/dollars out of the AAA staff.  Allow yourself at least a month lead time.  We recommend giving them the spreadsheet in the Appendix and having them fill in the actual numbers.  This approach will force them to use the same categories for each expense year by year.

The Section usually charges a late fee for registrants that do not register by the date publicized on the registration form.  The major reason for this is to motivate people to book their whole trip in advance.  In particular, to have them book the hotel in advance.  The AAA pays penalties if less than 80% of the block of rooms is not booked for the conference.

Note that in working with the spreadsheet, not all the people attending the conference pay the registration fee.  In particular, all doctoral students, the AAA staff, and the plenary speakers (with waivers) do not pay the registration fee.  The spread sheet contains a simple CVP analysis for the conference.  The second page of the spreadsheet calculates the breakeven number of attendees for the conference.  The breakeven calculation is a bit more complex than normal since the outside contributions directly reduce the fixed costs, and the meals for the non-paying attendees increases the fixed costs.

The current spreadsheet can be tweaked for scenario analysis.  You can change the cost inflation % in F2, the number of registrants in E4, or the fee mix in E10, and have the changes flow through the spreadsheet and adjust the breakeven numbers.  As you can see from our analysis, our goal was not to breakeven, but to lose no more than the prior year's conference.

Note 8.  Obtaining Sponsors

Several organizations have traditionally sponsored part of the conference.  Usually the sponsors are textbook publishers.  You will need to contact the AAA Meeting Coordinator to find out the usual suspects and contact them fairly early.

Note 9.  Evaluating the Papers

The number of papers submitted will determine the quality of the final papers accepted.  If you want a high quality conference, you need to have a large number of papers submitted.  This is why it is crucial to advertise, send out several blast e-mails, and call up many people to see if they plan to submit a paper to the conference.

This is primarily the task of the JIS Editor and the Conference Only Coordinator.  They jointly determine which papers will be accepted for presentation at the conference and which will be accepted for the Forum Session.  Papers that are not accepted for presentation at the regular meeting are usually accepted for the forum.

The JIS Workshop Coordinator handles the paper submission and review process individually.

Note 10.  Forming the Program

An overview of the philosophy.

The organizers should consider research in a very broad sense.  Participants are usually very interested in what’s happening in practice. If you can incorporate practitioners in a panel, or as a speaker, this is usually a very nice option.

The IS section has also favored giving doctoral students and junior faculty as much opportunity as possible to participate in the program.  Thus, we usually choose all doctoral students as moderators and as many doctoral students and junior faculty as possible for paper presentations and as discussants.  This allows them to become acclimated to the Section early in their careers and will hopefully nurture their development and growth as AIS educators and researchers.

An overview of the mechanics.

The JIS Editor and the Conference-Only Coordinator determine which papers will be accepted for presentation in a teleconference.  They will try to group papers in sessions according to topic.  Next they look at the mix of papers in a time slot, both from a methodology standpoint and education vs. academic standpoint.  We also make an attempt to mix education and academic papers together in concurrent sessions, based on responses from the 2003 meeting.  We learned that attendees like sessions mixed with education and academic papers.

In 2004 we also scheduled concurrent sessions to allow participants as much choice as possible.  We have now grown to the point where the meeting is big enough to sustain concurrent sessions.  Remember to come up with titles for the sessions beyond just “Concurrent Session A” etc.  This helps the participants see quickly what each session is about and decide which session they want to attend.

Discussants are also selected in the teleconference.  Usually they are reviewers from the initial screening of papers.  The Conference-Only Coordinator emails potential discussants to determine whether they are willing to serve in this role.  Once all the discussants are lined up, the Conference-Only Coordinator emails all authors of research papers only to inform them of their discussant and remind them of the session format.

The Conference-Only Coordinator also assigns moderators for all sessions.  An e-mail distribution list for discussants, moderators, and authors will help stay in contact with these individuals.

The program must be carefully checked for spelling errors, author names left off, school affiliations, and acknowledgements.  Also circulate the program to the planning committee.  The more eyes that look at it, the better.  The program must be sent to AAA by their deadline to have it printed and stuffed in registration packets.

The conference evaluation form should also be drawn up by the program chair.  All sessions and meals are evaluated.

Note 11.  Guidelines for Best Paper Awards

The Editor of JIS and the Conference-Only Paper Coordinator will promptly decide (approximately the second week in October) which papers will be considered for Best Paper Awards.  Once this decision is made, the research papers (and all of the appropriate reviewer comments) will be sent electronically to the Research and Publications Committee Chair.  Similarly, the education papers that have been nominated for the Best Paper Award will be sent to the Education Issues Committee.  Each Committee will decide the criteria that they want to use for selecting one best research paper and one best education paper. After each Committee has established the criteria, if the consensus is that the papers in either category are not high enough quality to merit “Best Paper Award’” then it would be better not to award a paper in that category.  Each of these committee chairs will advise the Program Chair of their decision not later than November 8th so that plaques can be prepared for presentation at the meeting. Starting with the 2006 Meeting, only plaques will be awarded to the winners.

Note 12.  Categorizing Sessions for CPE Credit

AIS New Scholar Consortium & JIS Research Workshop

8:00 a.m. – 5:00 p.m.	CPE Workshop, Semantic Modeling of Accounting Phenomena

Julie Smith David, Arizona State University
Bill McCarthy, Michigan State University

(Management – IS)

8:00 – 10:00 a.m.		Approaches to teaching AIS    (Management – IS)

Panelists: Peter Gillett, Greg Gerard, David Fordham, Marcus Odom

- REA approach, Transaction cycles, Projects, Cases

10:00 – 10:15  a.m.		Break

10:15 a.m. – Noon		Research tips for new scholars  (Acct /Audit – Research)

Panelists:  Paul Steinbart, Jim Lampe, Robin Pennington,    
                                    Antoinette  Lynch

1:15– 1:45 p.m.	Software/tools for running Web experiments  (Management – IS)

Bob Slater, Texas A&M University – Corpus Christi

1:45 – 2:30 p.m.	Concurrent Sessions   (Personal Development)

2:30 – 5:00 p.m.	JIS Research Workshop   (Acct /Audit – Research)

Friday, January 6, 2006

8:30 – 10:00 a.m.  	Welcome and Plenary Session

Welcome and Introduction

Carolyn Strand Norman, VA Commonwealth University

Plenary Speaker

A Conversation with AAA President-Elect Shyam Sunder,

James L. Frank Professor of Accounting, Economics, and Finance,

Yale University

(Acct /Audit – Research)

11:00 a.m. - Noon	Concurrent Paper Session A   (Acct /Audit – Research)

Moderator:  Jan Eighme, Miami University

EDGAR Extraction System: An Automated Approach to Analyze Employee Stock Option Disclosures

Gerry Grant (California State University – Fullerton) and 
                          Sumali Conlon (University of Mississippi)

Discussant:  Mark Cecchini, University of South Carolina

Influences on Home Computer Security Intentions and Behavior

Amy Ray, Mary Culnan and Ellen Foxman (Bentley University)

Discussant:  Jacob Peng, University of Michigan – Flint

Concurrent Paper Session B (Management – IS)

Moderator:  Ron Clark, Auburn University

End User Query Performance: The Effect of User Characteristics in the Presence of Information Request Ambiguity

Neal Ashkanasy, Fiona Rohde, Paul L. Bowen and Chiu Yueh Alice Wu (The University of Queensland)

Discussant: Maureen Mascha, Marquette University

Use of Knowledge Management Systems and the Impact on Declarative Knowledge Acquisition

Holli McCall (University of Connecticut), Vicky Arnold and Steve G. Sutton (University of Central Florida)

Discussant: Diane Janvrin, Iowa State University

Noon – 1:45 p.m.	Luncheon

Announcements – Stephanie M. Bryant, President, IS Section

Speaker and Best Paper Awards – Brad M. Tuttle, Professor, University of South Carolina and Editor, Journal of Information Systems 
(Acct /Audit – Research)

2:00 – 3:30 p.m.	Concurrent Paper Session C (Management – IS)

Moderator: Partha Mohapatra, Morgan State University

Policy-Level Specifications in REA Enterprise Information Systems

Guido Geerts (University of Delaware) and William E. McCarthy (Michigan State University)

Discussant:  Del DeVries, University of Tennessee

The Effects of Data Model Representation Method on Task Performance: An Experimental Investigation

Robert Fuller, Uday Murthy, and Brad Schafer (University of South Florida)

Discussant:  Tina Loraas, Auburn University

Concurrent Paper Session D (Acct /Audit – Research)

Moderator: Marianne Bradford, North Carolina State University

Does a Continuous Audit Lead to a Lower Cost of Debt Capital? An Experiment of Commercial Loan Officers

DeWayne L. Searcy (Auburn University), Terry J. Ward (Middle Tennessee State University), and Jon B. Woodroof (University of Tennessee)

Discussant:  Jagdish Pathak, University of Windsor

Signal Words and Signal Icons in Application Control and Information Technology Exception Messages

Tarek Amer and Jo-Mae B. Maris (Northern Arizona University)

Discussant:  Robin Pennington, University of Tennessee

4:00 – 5:30 p.m.    	Concurrent Paper Session E (AI/ET Sponsored) - (Acct /Audit –

Research) Panel Discussion:  Research in AIS Security and Audit

Moderator:  Greg Gerard, Florida State University

Concurrent Paper Session F  (Management – IS)

Moderator: Dwayne N. McSwain, Middle Tennessee State University

Information Filtering: Converting data into relevant info for decision making

Tanya Lee (University of North Texas) and Del DeVries (University of Tennessee)

Rationalizing Wireless Calling Plans: Querying a Database to Detect Billing Errors and Analyze Calling Pattern

A. Faye Borthick (Georgia State University) and Donald R. Jones (Texas Tech University)

The United States Department of the Treasury Bureau of Engraving and Printing Tests an E-Procurement System

Ulric Gelinas and Janis L. Gogan (Bentley University)

8:30 – 10:00 a.m.  	Forum Papers  (Acct /Audit – Research)

8:30 – 10:00 a.m.  	Concurrent Paper Session G (AI/ET sponsored) –

(Acct /Audit – Research)

Moderator: Kenneth Henry, Florida International University

Increasing Student Accuracy in FARS Database Searching

Margaret R. Garnsey, John O’Neil, and Leonard Stokes (Siena College)

Discussant:  Ingrid Fisher, State University of New York –

Albany

Interpretable Credit Model Development via Artificial Neural Networks Brad S. Trinkle and Amelia A. Baldwin (University of Alabama)

Discussant:  Bonnie Morris, West Virginia University

10:30 – Noon	Concurrent Paper Session H  (Acct /Audit – Research)

Moderator:  Sarah Bee, Seattle University

Understanding the Benefits and Uses of Generalized Audit Software

Michele Matherly (University of North Carolina – Charlotte), Marcia L. Weidenmier (Mississippi State University), and Susan H. Ivancevich (University of North Carolina – Wilmington)

Business Disaster and Recovery Planning: An Illustrative Case Corporate Accounts Payable Department

Sally Webber and Bill Cummings (Northern Illinois University)

Evaluating Controls in Accounting Software

Constance M. Lehmann and Cynthia D. Heagy (University of Houston – Clear Lake), and Carolyn S. Norman (Virginia Commonwealth University)

Concurrent Paper Session I  (Management – IS)

Moderator: Kathy Hurtt, Baylor University

A Meta-Analysis of the Effects of IT Investment on Financial Firm Performance

Jee-Hae Lim, University of Kansas

Discussant:  Linda Ruchala, University of Nebraska

The effect of ERP system implementations on the usefulness of accounting information

Joseph Brazel (North Carolina State University) and Li Dang (Oregon State University)

Discussant:  Darrell Brown, Portland State University

Noon – 1:30 p.m.	Luncheon

Speaker:  William E. McCarthy, Professor, Michigan State University

and Arthur Andersen Alumni Professor

(Acct /Audit – Research)

1:30 – 3:00 p.m.	Hot Topics for AIS Research   (Management – IS)

Facilitator: 	Chris Wolfe, Texas A&M University

Panelists:       Jim Hunton, Bentley University

Dan Stone, University of Kentucky

Steve Sutton, University of Central Florida

3:00 – 3:30 p.m.	Closing Session  (Management - IS)

Stephanie M. Bryant, President, IS Section 
Dan R. and Tina P. Johnson Distinguished Professor of Accounting, 
University of South Florida

Note 13.  Making Papers Available in Advance of the Conference

In 2004 we posted the papers at the IS section web site a couple of weeks prior to the meeting.  We then sent a blast email to the membership telling them the papers were there and advising them that this was the only version of the papers they would receive.  This allows people to download and read the papers prior to the meeting.  In the future, we need to be sure this site is password protected, as there may be copyright issues.  Additionally, authors may not want their working papers posted in this manner.  Future conferences should definitely address this issue.

In 2006, all papers will be posted by December 2nd so that attendees may read the papers of interest prior to the sessions.

Note 14.  Final Hotel Details

- Menu.  There are several minor details that need to be worked out with the hotel.  The first is the menu for the breakfasts/luncheons.  While the standard menu is a function of price, it is an excellent idea to work out a somewhat more elaborate vegetarian menu.  The standard vegetarian menu at most hotels is dreadful and a bit more care on this selection will pay off.

- AV Requirements.  Starting with the 2006 Meeting, the planning committee decided to solicit members in the area of the Meeting to bring laptops and portable projectors to save the cost of renting this equipment from the conference hotel.  Therefore, for the 2006 Meeting and forward, we will advertise to all presenters, discussants, and attendees that no overhead projectors will be available.  Presenters and discussants will be expected to bring their presentations on thumb drives.  We will only rent screens from the hotel.

  - To support this initiative, a Technology Manager was selected at the 2006 Meeting and agreed to hold this position for three years. In exchange for this service, his registration fee will be waived for the Midyear Meeting for each of these years of service.

APPENDIX A

Planning Document

2006 AAA-IS Midyear Meeting

| I. Meeting Logistics Meeting Location: Scottsdale, AZ Dates of Meeting: January 4-7, 2006 Wed. evening, Jan. 4 - Reception for attendees of AIS New Scholar Consortium Thursday 8-5:30, Jan. 5 - AIS New Scholar Consortium Friday, Jan. 6 through 3pm Saturday, Jan. 7 - Official Midyear Meeting Hotel: Doubletree Paradise Valley Resort, Scottsdale, AZ Estimated room cost: $149/night Cutoff date for room reservation: December 5, 2005 Paper Deadline: September 15, 2005 II. Key Personnel |
| --- |
| Role | Who (Affiliation) | Phone | Email |
| IS Section President | Stephanie Bryant (Univ. of S. Fla.) | 813-974-6550 | sbryant@coba.usf.edu |
| Meeting Program Chair | Carolyn Strand Norman (VA Commonwealth U) | 804-828-3160 | castrand@vcu.edu |
| AIS New Scholar Consortium | Uday Murthy (Univ. of South Florida) Tanya Lee (University of North Texas) |  | umurthy@coba.usf.edu leet@unt.edu |
| Paper Coordinator, Joint Submissions | Brad Tuttle (University of South Carolina) | 803-777-6639 | jis@usc.edu |
| Paper Coordinator, Conference Only Submissions | Mary Curtis (University of North Texas) | 940-565-3092 | curtism@unt.edu |
| Paper Coordinator, AIS Education Papers | Conni Lehmann (Univ of Houston-Clear Lake) |  | Lehmann@uhcl.edu |
| AI/ET Paper Coordinator |  |  |  |
| AAA Meeting Coordinator | Dee Strahan | 407-366-9855 | deestrahan@atlantic.net |

Planning Document

2004 AAA-IS Midyear Meeting

APPENDIX A

Paper Submission Process (2006)

Papers submitted jointly to the conference and JIS go to Brad Tuttle, who will send these papers out to reviewers from the JIS editorial board.  Papers submitted to the conference only will go to Mary Curtis, who will send these papers to reviewers.  She will forward papers that are primarily focused on AIS education to Conni Lehmann, who will send these papers out to reviewers.

DEADLINES Used for the 2006 MID-YEAR MEETING

All papers to reviewers by (confirm receipt):        			Monday, September 19, 2005

Moderators assigned by:						Friday, September 30, 2005

Reminders to reviewers (Mary):           				Week of October 7, 2005

All reviews completed by:         					Friday, October 14, 2005

Conni follows up on reviews (for Mary):			         	Week of October 17, 2005

Brad/Mary conference call:                     				October 25/26, 2005 

Draft of Sessions:                            					Friday, October 28, 2005 

Top 3 papers in each category to Cmte for decision on

Best Paper Awards:                                              			Friday, October 28, 2005

(Set deadline to get winners names/paper titles to AAA

to have plaques made)

Authors notified by:                           					November 2, 2005 

Discussants assigned by:                   					November 2, 2005 

Deadline for authors to agree to present/forum              		Tuesday, November 8, 2005

Authors notified of discussant          					Friday, November 11, 2005  

Final Draft of Sessions to Program Chair:	                 		Friday, November 11, 2005 

Final version of paper to discussants and to Mary:          		Friday, December 2, 2005

(also posted on web site)

Receptions

For the 2004 meeting, the Friday night reception was on the Show Queen Riverboat, which was within walking distance of the hotel in Clearwater. For the 2005 Meeting, which was in New Orleans, we did not have a main attraction for the reception so that attendees could experience the city as they chose.  Similarly, since the 2006 Meeting is in Scottsdale, AZ and minutes away from historic Old Town Scottsdale, the Thursday and Friday night receptions were very light refreshments so that attendees may visit a restaurant of their choice for dinner.

Plenary Session Speaker

The tradition is to have the AAA President speak at the plenary session.  This is a good tradition because it brings the prestige of the national organization to our group and helps that individual become more familiar with our section and its members.

Other Speakers

The JIS Editor is usually asked to speak at either the Friday or Saturday lunch, regarding the status of the Journal and submissions.  This is also an opportunity for the Editor to announce the winners of the Best Paper Awards.

Budget

A worthy goal is to come close to break even on the meeting.  Start with the budget from the prior year.  Make the Wednesday, Thursday, and Friday night receptions light refreshments.  This should save a substantial amount of money.  Additionally, for the AIS New Scholar Consortium, we will have only peanuts and pretzels, as most people will go to dinner anyway.

We plan to again subsidize the doctoral students who are members of the IS section by waiving their registration fee.  For the 2003 and 2004 meetings, this cost the section roughly $3800 (19 registrants * $200 registration fee waived) for just the foregone registration fee.  As of 2004, there were 103 student members in the IS section. While the doctoral consortium is expensive to support, the Executive Committee believes it is worthwhile to provide this resource for those individuals.

Financial Support

For the 2003 midyear meeting, Nancy raised approximately $5,000 of external funding.  For the 2004-2006 Meetings, Stephanie obtained funding from the KPMG Foundation.

Annual AIS New Scholar Consortium

Our goal is to offer a program that will draw people back year after year.  That means that we can’t craft a program that is heavily geared to “soft” topics like time management etc. What people need the most help with is research, and as such, the consortium should reflect that emphasis.  Additionally, it was suggested in the Executive Committee to open this consortium to first and second year AIS faculty members, as they could undoubtedly benefit from a consortium.  Thus, we have renamed the doctoral consortium the “AIS New Scholar Consortium” to reflect the inclusiveness of the new faculty members.  The Program includes the topics covered and times allotted to each topic for the Consortium, which is held on the Thursday prior to the regular Meeting.

Web Site Updating

See the Timeline, starting on page 8 to determine what needs to be placed on the IS Section website and the AAA website, along with the times that this information should be posted.

GENERAL PROGRAM OUTLINE

Wednesday, 1/7/04

6:00 p.m. – 7:30 p.m.		AIS New Scholar Consortium Reception

Thursday, 1/8/04

7:00 a.m. – 8:00 a.m.		AIS New Scholar Consortium Continental Breakfast

8:00 a.m. – Noon		Consortium Program

Noon – 1:30 p.m.		Luncheon

1:30 p.m. – 5:30 p.m.		Consortium

6:00 – 7:30 p.m.		Early Bird Welcome Reception

Friday, 1/9/04

7:30 a.m. – 8:30 a.m.		Continental Breakfast

8:30 a.m. – 10:00 a.m.		Welcome and Plenary Session

10:00 a.m. –10:30 a.m.	Coffee Break

10:30 a.m. – Noon		Sessions

Noon – 1:30 p.m.		Luncheon

1:30 p.m. – 3:00 p.m.		Sessions

3:00 p.m. – 3:30 p.m.		Coffee Break

3:30 p.m. – 5:00 p.m.		Sessions

6:00 p.m. – 7:30 p.m.		Reception

Saturday, 1/10/04

7:30 a.m. – 8:30 a.m.		Continental Breakfast

8:30 a.m. – 10 a.m.		Forum Papers

10:30 a.m. – Noon		Sessions

Noon – 1:30 p.m.		Luncheon

1:30 p.m. – 3:00 p.m.		Special Topics Forum

3:00 p.m.			Closing Remarks

Search AAA Home About AAA Membership Sections / Regions Meetings Calls For Papers Publications Faculty Development Teaching Research Practice Service Awards Placement Marketplace Links & Organizations Meeting Logistics The Meeting Office is responsible for all logistics of the meeting, providing comprehensive instructions to the hotel detailing all logistics of the meeting including but not limited to meeting rooms' setup, audiovisual needs, food and beverage requirements, function rooms' setup, staging if required, billing information, exhibit requirements if appropriate, and any additional special logistical requirements. It is important that all logistics requirements be processed through the Meeting Office to avoid confusion on the part of the hotel staff, to ensure that the meeting is managed properly on site, and that charges are not incorrectly posted to the master account. The Meeting Office also arranges for registrations to be processed and badges prepared for all pre-registered attendees and speakers. Exhibitor registrations (where applicable) are also processed by the Meeting Office and appropriate credentials provided to exhibitors. Continuing Professional Education registrations are processed and a list of workshop attendees is provided to the presenter. The Meeting Office provides on-site management of the meeting, resolving any problems that may arise in the course of the conference. Meeting staff distribute conference materials, process on-site registrations, post signage, and place sign-in and sign-out forms in each meeting room prior to the start of the session and retrieve forms following the conclusion of the session. The on-site Meeting Manager also assists meeting attendees by interfacing with the hotel as required. Based on the program chair’s goals for type of event and food desired, the Meeting Office recommends menus that will provide the event desired at the most cost-effective price. With direction from the program chair, the Meeting Office estimates food and beverage requirements and recommends menus, coordinating with hotel catering staff to ensure the overall quality of the event. Registration figures are closely monitored and appropriate food and beverage guarantee figures are provided to the hotel by the Meeting Office. Production of tickets for luncheons or other events will be handled by the Meeting Office and counts monitored for hotel food and beverage guarantees. The on-site Meeting Manager continuously monitors food and beverage functions, ensuring that what was ordered is delivered, that quality is maintained, and that charges are correctly applied to the master account. General & Financial Meetings & Awards Publications Forms List Manual Index

Search AAA Home About AAA Membership Sections / Regions Meetings Calls For Papers Publications Faculty Development Teaching Research Practice Service Awards Placement Marketplace Links & Organizations Meeting Content The program chair is responsible for the content of the technical program, such as determining the type and number of general sessions and breakout sessions and food and beverage functions. The program chair invites and confirms speakers and relays any special speaker requirements, including audiovisual needs, to the Meeting Office for inclusion in the logistics of the meeting. The program chair should provide the Meeting Office with a list of complimentary registrations and names of plenary and luncheon speakers at least three weeks prior to the meeting so that name badges may be prepared in advance. The final program should be forwarded to the Meeting Office 45 days prior to the meeting to enable the Meeting Office to develop meeting room specifications and assignments as well as determine signage requirements. It is not uncommon for the headquarters office to receive calls from members about upcoming meetings and if we have your program information, we can better meet your needs. Audiovisual requirements for general sessions must be conveyed to the Meeting Office as larger sessions often require different equipment for an effective presentation. Most frequently, overhead projectors and screens are assigned to each breakout room but other equipment must be specifically requested in advance. The Treasurer and Regional or Section Meeting Program Director should determine, in advance, if any CPE workshops are to have net proceeds shared with sponsoring Sections or other groups or individuals, and advise the Sarasota office staff in order to ensure proper allocation of revenue and expenses (Form 10). As some states require an additional sign-in (Form 11) and sign-out (Form 12) procedure along with the conference CPE form (an example is provided as Form 13), the program chair should arrange for preparation of sign-in and sign-out sheets and folders. The CPE form for each meeting should be reviewed by AAA headquarters before it is made final. Additional information will be sent to 2003 Region and Section program chairs in September or October 2002; this material will include time frames for copying and mailing to be done through AAA headquarters. Contact Education Project Manager Linda Watterworth at the AAA headquarters for information and assistance: Linda Watterworth Education Project Manager American Accounting Association 5717 Bessie Drive Sarasota, FL 34233-2399 Voice: (941) 921-7747 ext. 318 Fax: (941) 923-4093 Email: linda@aaahq.org General & Financial Meetings & Awards Publications Forms List Manual Index

Contact AAA Staff

Search AAA Home About AAA Membership Sections / Regions Meetings Calls For Papers Publications Faculty Development Teaching Research Practice Service Awards Placement Marketplace Links & Organizations Publicity and Registration Administrative staff can assist in publicizing a conference at various stages (Call for Papers, registration period, etc.). To arrange for newsletter or Web exposure, contact Associate Director of Communications Beverly Harrelson at the AAA headquarters: Beverly Harrelson Associate Director of Communications American Accounting Association 5717 Bessie Drive Sarasota, FL 34233-2399 Voice: (941) 921-7747 ext. 309 Fax: (941) 923-4093 Email: beverly@aaahq.org Staff also handle registrations received via mail, fax, or other methods. Beginning with 1999 meetings, each Region and Section may offer Web-based electronic registration to attendees. There is no charge to Sections or Regions for this service. Credit card payments may be handled online through the AAA’s web site. An example meeting registration form is provided (Form 14). The registration form for each meeting should be reviewed by AAA headquarters before it is made final. General & Financial Meetings & Awards Publications Forms List Manual Index

Search AAA Home About AAA Membership Sections / Regions Meetings Calls For Papers Publications Faculty Development Teaching Research Practice Service Awards Placement Marketplace Links & Organizations Programs and Meeting Material The Publications Department at the AAA headquarters is available to arrange for preparation and printing of such materials as the final Program, Proceedings (if any), Evaluation Form, and CPE form. The program chair should arrange the delivery dates of final copy for each of these materials well in advance of the meeting, to ensure that workload demands do not delay or reduce the quality of the final product. As a general rule, complete materials to be used at a meeting must be provided 45 days prior to the meeting. However, production time depends on the size (number of pages) and quantity desired, as well as on workload and other factors. We request an electronic copy of such materials as the meeting program, abstracts, etc. If AAA staff are to design, layout, and proof abstracts or similar material, additional production time will be needed. The normal source of material included in various meeting publications is shown below: Program Electronic copy from program chair Abstracts Reproducible hard copy (or, for staff design and layout, electronic copy) from program chair List of Registrants Generated from AAA registration records Evaluation Form Prepared from program information; program chair may specify special material desired CPE Credit Form Prepared from program information Hotel Map Reproducible hard copy from program chair Tent Cards Prepared from program information Sign-In and Sign-Out Forms Prepared from program information Contact Assistant Director for Publications Diane Hazard at the AAA headquarters for information and assistance: Diane Hazard Assistant Director for Publications American Accounting Association 5717 Bessie Drive Sarasota, FL 34233-2399 Voice: (941) 921-7747 ext. 307 Fax: (941) 923-4093 Email: diane@aaahq.org General & Financial Meetings & Awards Publications Forms List Manual Index

Search AAA Home About AAA Membership Sections / Regions Meetings Calls For Papers Publications Faculty Development Teaching Research Practice Service Awards Placement Marketplace Links & Organizations Finalizing Events Prior to finalizing the number of events and concurrent sessions, the program chair should confirm with the Meeting Planner the amount of meeting space being held at the hotel for the group. Any deviation from the program, as outlined in the Site Search Request Form, should be reviewed to determine that there is sufficient meeting space available at the hotel to accommodate the change. Meeting space and sleeping rooms are blocked in the hotel contract based on the program flow submitted on the Site Search Request Form. The hotel’s anticipated revenues influence the conduct of the negotiations. Subsequent shifts in plans can cause problems that are best resolved if identified as far in advance as possible. For example, one group’s traditional meeting pattern had a general session and six concurrent sessions held on one day of a two-day meeting with only a general session the second day. If a subsequent program chair decides (long after the contract had been signed) to substitute a general session and eight concurrents on the first day and a general session and four concurrents on the second day, possible problems that could be anticipated include: (1) no additional meeting space may be available as the remainder of the hotel’s meeting space may be committed to other groups; (2) the hotel may not have meeting space large enough to accommodate the additional two concurrents; and (3) if the hotel does have space, rental charges are likely to be assessed based on the additional space to be used. It is important that the program chair discuss any desired changes with the Meeting Planner at the beginning of the development process to enable the Meeting Planner and the Executive Director to negotiate changes with the hotel to accommodate a different program as cost-effectively as possible. General & Financial Meetings & Awards Publications Forms List Manual Index

# APPENDIX B

AMERICAN ACCOUNTING ASSOCIATION

# SITE SEARCH REQUEST FORM

To initiate a site search, please complete this form and fax to Linda Watterworth at (941) 923-4093 or email (linda@aaahq.org). A site search will be conducted at no charge for up to 3 locations and 2 sets of dates. The meeting office will compile a report summarizing the responses received and how well the meeting space offered fits your planned program. Completion of the report varies depending on response time of hotels and meeting staff commitment to current association meetings.

CONTACT INFORMATION

Group Name: 	IS Section

Program Chair:   Mary Curtis

Address: 	  Accounting Department, P.O. Box 305219, University of North Texas

Denton, TX  76203

Phone: 940-565-4366                                                               Fax:  940-565-3803

Email:  curtism@unt.edu

### SITE INFORMATION

Year: 2007       Preferred Dates:   January 3-6, 2007   		Secondary Dates: January 10-13

City, State: 	(1) Savannah, GA      	(2) Charleston, SC		(3)  San Antonio, TX

Preferred Location:     downtown

Number of Attendees Expected:      125	      *Number expected to stay in hotel:    100

*Your best estimate of this number will help in the negotiation of the contract for your meeting. Hotels base room rates and rental rates for meeting rooms on the number of guest rooms the group will use. Typically your group will be responsible for 80% of the hotel guest room nights in your contract. Your group will be obligated to pay the difference between 80% and actual use of guest rooms, so realistic estimates are important.

PROGRAM INFORMATION

A comprehensive outline of your program format is needed so that meeting specifications provided to the prospective hotels accurately reflect the amount of meeting space you believe you will need. Be sure to list Type of Event such as CPE Workshops, General Sessions, Number of Breakouts per time period, Breakfasts, Lunches, Receptions, and whether there is a Paper Forum, Doctoral Consortium, and/or Exhibit area planned. If your format will be the same as a previous program, please indicate below and attach a copy of that program outline.

Complete the Meeting Program Event Schedule on the next pages. If additional days are needed, copy one of the Meeting Program Event pages, or copy and paste additional days in Word document. If there are additional events not included in form, feel free to add those events on the appropriate day.

Doctoral Consortia: Meetings that offer a Doctoral Consortium should complete Doctoral Information on last page.

Meeting Program Event Schedule

DAY 1 – please indicate which of the following events will occur on this day.

Type of Event:  AIS New Scholar Consortium Reception         (approximately 50 attending)

Reception 	 Time:   6:00 – 8:00 PM

Light snacks

DAY 2 – please indicate which of the following events will occur on this day.

Type of Event:  AIS New Scholar Consortium

Breakfast	Time:  7:00 – 8:00 AM   Number of attendees: 80-90

Lunch 		Time:  Noon – 1:30 PM  Number of attendees: 70-80

General/Plenary session 	Time:  8:00 AM – 5:30 PM

(approximately 60 people attending) For the morning session, all attendees will be in the same room - prefer rows of tables facing one direction. For afternoon session, we will need the room re-set with round tables for discussion with room for approx 8-10 people at each. For a short time, 1:45 to 2:30, we will need a second room for half of the attendees to meet in.

SMAP session	Time:  8:00 AM – 5:30 PM   Number of attendees: 22

Room for Executive Committee Meeting:  1:30 – 5:00 PM   (approximately 20 people attending)

Reception 	Time:  5:30 – 6:30 PM   Number of attendees: 60-70, Light snacks

Note: Coffee breaks will be scheduled mid-morning and mid-afternoon, based on session schedule.

DAY 3 – please indicate which of the following events will occur on this day.

Type of Event:   Regular IS-Section Midyear Meeting Begins

Breakfast	Time:  7:30 – 8:30 AM   Number of attendees: 130-135

Lunch 		Time:  Noon – 1:30 PM Number of attendees: 140

General/Plenary session 	Time:  8:30 – 10:00 AM                 (approximately 150 attending)

Concurrent breakout sessions (quantity is optional, specify if known) 	Yes

1 Timeslot –  # Rooms  2              Qty each room  75	 Time:  10:30 AM – Noon

2 Timeslot –  # Rooms  2    	Qty each room  75	 Time:  1:30 – 3:30 PM

3 Timeslot –  # Rooms  2    	Qty each room  75	  Time:  4:00 – 5:30 PM

Reception 	Time:  5:30 – 6:30 PM                   (approximately 125 attending)

Light snacks

Note: Coffee breaks will be scheduled mid-morning and mid-afternoon, based on session schedule.

DAY 4 – please indicate which of the following events will occur on this day.

Type of Event:  Regular IS-Section Meeting

Breakfast / Paper Forum	Time:  7:30 – 8:30 AM    Number: 12 rounds of 10 chairs each

Lunch 		Time:  Noon – 1:30 PM  Number of attendees: 130

Paper Forum 	Time:  8:30 – 10:00 AM   (see breakfast above)

Concurrent breakout sessions (quantity is optional, specify if known) 	Yes

1 Timeslot –  # Rooms  2	Qty each room   75 	Time: 10:00 AM – Noon

2 Timeslot –  # Rooms  2	Qty each room   75	Time: 1:30 – 3:00 PM

Other events:        Closing Session             Time: 3:00 – 4:00 PM       (approximately 150 people attending)

Note: Coffee breaks will be scheduled mid-morning and mid-afternoon, based on session schedule.

APPENDIX C

Call for papers

2007 AAA-IS Section Mid-Year Conference

January 3-6, 2007

Savannah, Georgia

The Information Systems Section of the AAA will hold its 2007 Mid-Year Conference in Savannah, Georgia. The meeting will include a plenary speaker, panel discussions, research paper sessions, education paper sessions and workshops, forum papers, the JIS Research Workshop. The 5th annual AIS New Scholar Consortium will precede the meeting.  Here is a quick outline:

        AIS New Scholar Consortium.  The 5th  annual AIS New Scholar Consortium will kick off with a reception on Wednesday evening, January 3rd.  The consortium is open to all AIS and IS doctoral students and to AIS professors who received their PhD after January 1, 2003.  Consortium attendees will meet on Thursday, January 4th and will receive advice from seasoned AIS faculty for successfully starting an academic career.  The IS section will once again waive the registration fee for the entire meeting for doctoral students who are members of the IS section.  This is made possible by a grant from the KPMG Foundation. Attendees may register for the consortium along with their meeting registration through the AAA online registration system.

        AIS Educational Workshops. There will be two AIS Educational Workshops this year, in addition to the education paper sessions. The first will be on Thursday afternoon, January 4rd, beginning at 2:00, and the second will be on Saturday afternoon, January 6th, immediately after lunch. All conference registrants are welcome to attend these workshops, free of charge. Watch the section web page for an announcement of the workshop topics.

        JIS Research Development Workshop. The JIS Research Development Workshop is scheduled for Friday morning, January 5th.  The purpose of this Workshop is to promote research by PhD students and faculty new to AIS research.  Workshop participants will discuss drafts of their working papers with members of the JIS Editorial Advisory and Review Board and with other workshop participants.  The workshop is structured to provide detailed feedback to further develop a working paper for future journal submission.  There is no obligation for the authors to submit their completed work to JIS, although JIS is one high quality journal outlet that does welcome conceptual, theoretical, and empirical AIS papers.

        Concurrent Sessions.  The 2007 meeting will have concurrent sessions featuring both academic research papers and education research papers.

        Research Forum.  This is an opportunity for authors to discuss their papers in an informal setting.

        Best Paper Awards.  The Research and Publications committee and the Education committee will select the Best Academic Paper and Best Education Paper Award winners in a blind review process. Award winners will be recognized during the conference. Winners of these awards will be extended an invitation to publish their paper in the Journal of Information Systems.

     Semantic Modeling of Accounting Phenomena (SMAP) CPE Session.  A SMAP workshop will be offered as a continuing professional education (CPE) session on Thursday, January 4th from 8:30 am – 5:00 pm.  The workshop will be led by Bill McCarthy and Julie Smith David.

Objective of the workshop:  This workshop provides a forum for researchers and educators interested in semantic modeling of accounting phenomena, as illustrated by the resources, events, and agents (REA) paradigm. The SMAP workshop is a seminar in that the discussion is lively yet informal. All participants are strongly encouraged to contribute teaching and/or research materials that they have developed.  Regardless of whether materials are for the classroom or research work-in-progress, they are welcome and should be submitted to julie.smith.david@asu.edu by December 1, 2006.  All submitted workshop materials will be shared through a private web site, and each participant will make a brief presentation of their work during the SMAP meeting.  Ideally, half of the contributions will be educational and half research - but the proportion of each is dependent on participants contributing materials!  Historically, the teaching materials have been shared to increase the data-modeling resources available to all, and to develop insights into problems frequently experienced in the classroom. Thus, if you have any REA problem sets, cases, or teaching tools and techniques, they would be much appreciated by the group.  Additionally, very preliminary research submissions are encouraged with the goal of providing detailed feedback early in the process.

Who should attend:  SMAP is designed for those interested in enhancing their REA expertise.  Participants in prior years have included faculty with limited experience in REA to faculty who are active in researching advanced REA issues.  Anyone interested in REA is encouraged to attend.

        AI/ET Involvement.  The AI/ET Section of the AAA will join the IS section in this meeting.  Some concurrent sessions will feature papers solely from the AI/ET membership.

Changes this year:

       	The Research and Education Committees will serve as reviewers for the research papers, select papers for presentation, and determine Best Paper Awards.

       	There will be a new education workshop on Thursday afternoon, available to all conference registrants, with topics of interest to experienced as well as novice AIS educators.

       	Note that submissions to the conference and to the Journal of Information Systems will be separate processes this year – the option for combined conference and journal submission will no longer be available.

Submissions:

       	All education and research paper submissions should be made, via email, to Sev Grabski (grabski@msu.edu) no later than September 1, 2006. Notification of acceptance to the conference will be made by November 1, 2006. Please note that submitted versions of the accepted papers will be posted to the section website.

       	JIS Workshop submission should be made, via email, to Margarita Lenk (margarita.lenk@colostate.edu) no later than October 1, 2006. Papers submitted for conference consideration should not also be submitted to the Workshop.

       	AI/ET submission: Greg Gerard (ggerard@cob.fsu.edu) and Ingrid Fisher (iefish119@aol.com) will be co-coordinators for the section papers this year. Please submit papers to both. A separate call for papers will be posted at the AI/ET section web site. Please find additional instructions for these submissions at: http://accounting.rutgers.edu/raw/aaa/aiet/aiethome.htm

If you have any questions about the meeting or suggestions on how to make the meeting for interesting for all, please don’t hesitate to email the conference chair, Mary Curtis (curtism@unt.edu).

PREVIOUS YEAR

CALL FOR PAPERS 
2006 AAA-IS Section Mid-Year Conference
January 5-7, 2006

Scottsdale, Arizona

The Information Systems Section of the AAA will hold its 2006 Mid-Year Conference in Scottsdale, AZ.  The meeting includes a plenary speaker, panel discussions, research and education paper sessions, and forum paper sessions.  We will also have concurrent research sessions for the AI/ET Section.  The “AIS New Scholar Consortium” will precede the meeting on January 4-5th.

Instructions for JOINT SUBMISSIONS (conference and Journal of Information Systems)

Due date:  September 15, 2005

Authors should submit research or education papers electronically to Brad Tuttle at jis@sc.edu.  The submission fee is $15, payable at https://aaahq.org/AAAforms/journals/jissubmit.cfm.  We strongly encourage early submission.  Authors should direct inquiries regarding manuscript submissions to Brad Tuttle (jis@sc.edu , 803-777-6639).  Authors will be notified regarding acceptance of manuscripts by November 4, 2005.  By November 21, 2005, authors of accepted submissions must provide the editor and designated session discussant a final electronic copy of their manuscript.

Instructions for Submission to the CONFERENCE ONLY

Due Date:  September 15, 2005

Authors should submit research papers, education papers, education cases, and education panel topics electronically to Mary Curtis at curtism@unt.edu .  Authors should direct inquiries regarding submission to Mary Curtis (curtism@unt.edu , 940-565-4366).  Notification of acceptance to the conference will be made by November 4, 2005.  By November 21, 2005, authors of accepted conference papers must provide a final electronic copy of their manuscript.

Instructions for Submissions for the AI/ET SECTION

A separate “Call for Papers” will be posted at the AI/ET section Web site.  If you are interested in submitting a paper for an AI/ET concurrent session, please find instructions for these submissions at the following site:  http://accounting.rutgers.edu/raw/aaa/aiet/aiethome.htm.

Instructions for Submission to the JIS New Scholars Research Workshop

Due Date:  September 15, 2005

A separate “Call for Papers” will be posted on the AAA Web site and the IS Section Web site for those interested in submitting a paper. This session is intended for New Scholars to get feedback from the JIS Editorial and Review Board in a friendly setting.  Dual submissions to the workshop and the main conference will be allowed. However, if your paper is accepted for a paper session at the main conference, it will be withdrawn from the workshop round table discussions.

For updates on the conference, please check the AAA-IS Section web site at http://aaa-is.byu.edu/, or contact the conference chair, Carolyn Strand Norman (castrand@vcu.edu , 804-828-3160).

APPENDIX D

NOT UPDATED YET

Call for Papers

Journal of Information Systems New Scholars’ Workshop

The Executive Committee of the Information Systems (IS) Section of the American Accounting Association announces the New Scholars’ research workshop immediately preceding the third annual mid-year meeting of the IS section.

Purpose.  The purpose of the workshop is to improve the research skills of Accounting Information Systems PhD students and faculty.  Members of the Journal of Information Systems Editorial Board will critique accepted workshop participants’ papers.  In addition, accepted workshop participants will receive two papers to review and critique.  At the workshop, participants will meet in small groups to discuss their work with the critiquing editorial board member and workshop participants.  The goal of this interaction is to develop submitted work for future journal submission.  Accepted workshop participants are not obligated to submit completed works to JIS.  Please consult the JIS website for a list of Editorial Board members (http://aaa-is.byu.edu/publications/jis/JIS_Editor_Staff.htm).

Where and When? The workshop is from 2:00 to 5:30 on January 8th, 2004 in Clearwater, Florida.  The submission deadline is September 1, 2003.

Selection Process.  Selection for the JIS Research Development Workshop is competitive.  Submitted papers: (a) should address issues related to information systems and (b) must not be currently submitted for publication at a journal.  Papers concurrently submitted to or scheduled for presentation at conferences are welcome.  Participation in the workshop is restricted to AAA IS section members.  Priority will be given to submissions from the following (in order of priority): Ph. D. students, untenured faculty, and researchers from outside the USA.

Application Process.  To apply, send a letter of submittal, an electronic copy of your paper, and an extended abstract of less than 500 words to the workshop coordinator, Bruce Dehning (bdehning@chapman.edu).  Applications must be received by September 1, 2003.  Papers (including text, references, figures, tables, and appendices) should be less than 30 pages in length (25 pages in A4 format), double-spaced, one inch (2.5 cm) margins, and 12 point Times or Times New Roman font.  The letter of submittal should affirm that the manuscript conforms to the submission policy outlined above:

- the manuscript is not under consideration, review, or has not been accepted for publication, and has not been published by any refereed journal or book.

- at least one of the authors is a member of IS Section of the American Accounting Association.

Receipt of submissions will be sent within 7 days.  Individuals selected as participants will be notified by November 1.  Please direct questions to the workshop coordinator, Bruce Dehning (bdehning@chapman.edu).

APPENDIX E

Conference Announcement

See You In Savannah

January 3-6, 2007

AAA-IS Section Mid-Year Meeting

The 2007 meeting will include a plenary speaker, panel discussions, research paper sessions, teaching sessions, forum papers, and the 5th annual AIS New Scholar Consortium.  Here is a quick outline:

        AIS New Scholar Consortium.  The 5th  annual AIS New Scholar Consortium will kick off with a reception on Wednesday evening, January 3rd.  The consortium is open to all AIS and IS doctoral students and to AIS professors who received their PhD after January 1, 2003.  Consortium attendees will meet on Thursday, January 4th and will receive advice from seasoned AIS faculty for successfully starting an academic career.

The JIS Research Development Workshop is scheduled for the afternoon of the New Scholar Consortium.  The purpose of this Workshop is to promote research by PhD students and faculty new to AIS research.  Workshop participants will discuss drafts of their working papers with members of the JIS Editorial Advisory and Review Board and with other workshop participants.  The workshop is structured to provide detailed feedback to further develop a working paper for future journal submission.  There is no obligation for the authors to submit their completed work to JIS, although JIS is one high quality journal outlet that does welcome conceptual, theoretical, and empirical AIS papers. 

The IS section will once again waive the registration fee for the entire meeting for doctoral students who are members of the IS section.  This is made possible by a grant from the KPMG Foundation.

        Concurrent Sessions.  The 2007 meeting will have concurrent sessions featuring both academic research papers and education research papers.

        Research Forum.  This is an opportunity for authors to discuss their papers in an informal setting.

        Best Paper Awards.   Reviewers will nominate papers for the Best Academic Paper and Best Education Paper Awards.  The Research and Publications committee and the Education committee will select the winners in a blind review process. Award winners will be recognized during the conference.

- Semantic Modeling of Accounting Phenomena (SMAP) CPE Session.  A SMAP workshop will be offered as a continuing professional education (CPE) session on Thursday, January 4th from 8:30 am – 5:00 pm.  The workshop will be led by Bill McCarthy and Julie Smith David.

Objective of the workshop:  This workshop provides a forum for researchers and educators interested in semantic modeling of accounting phenomena, as illustrated by the resources, events, and agents (REA) paradigm. The SMAP workshop is a seminar in that the discussion is lively yet informal. All participants are strongly encouraged to contribute teaching and/or research materials that they have developed.  Regardless of whether materials are for the classroom or research work-in-progress, they are welcome and should be submitted to julie.smith.david@asu.edu by December 1, 2006.  All submitted workshop materials will be shared through a private web site, and each participant will make a brief presentation of their work during the SMAP meeting.  Ideally, half of the contributions will be educational and half research - but the proportion of each is dependent on participants contributing materials!  Historically, the teaching materials have been shared to increase the data-modeling resources available to all, and to develop insights into problems frequently experienced in the classroom. Thus, if you have any REA problem sets, cases, or teaching tools and techniques, they would be much appreciated by the group.  Additionally, very preliminary research submissions are encouraged with the goal of providing detailed feedback early in the process.

Who should attend:  SMAP is designed for those interested in enhancing their REA expertise.  Participants in prior years have included faculty with limited experience in REA to faculty who are active in researching advanced REA issues.  Anyone interested in REA is encouraged to attend.

        AI/ET Involvement.  The AI/ET Section of the AAA will join the IS section in this meeting.  Some concurrent sessions will feature papers solely from the AI/ET membership.

APPENDIX F

# Hotel Information for the 2006 Meeting

Hotel Information

Doubletree Paradise Valley Resort
5401 N. Scottsdale Road
Scottsdale, Arizona  85250-7090
Toll-free Reservations:  1-877-445-6677
Tel: 1-480-947-5400
Fax:1-480-946-1524

www.paradisevalley.doubletree.com

The Doubletree Paradise Valley Resort hotel offers luxury, resort amenities, and visually stunning Sonoran Desert views on 22 acres of lush, tropical paradise, just minutes from historic Old Town Scottsdale and Arizona State University.  Renowned for its Frank Lloyd Wright-inspired architecture, sparkling fountains and water features, this warmly rustic yet sophisticated resort hotel features fine dining and casual cuisine, two large outdoor heated pools with whirlpools, a full health club, luxurious spa treatments, racquetball courts, a nine-hole putting green and on-site golf specialist, tour services and more.  The hotel is located 12 miles northeast of the Phoenix Sky Harbor International Airport.

Block Rate:  A limited number of rooms have been reserved for the conference rate of $149/night.  PLEASE make your reservations as early as possible to take advantage of this special room rate.  This rate is available until December 5, 2005.  When you register, use the Group/Convention Code: AAA.

The hotel requires that all reservations be guaranteed by major credit card.  Individual guest room deposits will be refunded if reservations are cancelled seventy-two(72) hours prior to the day of arrival.  If you do not cancel prior to the 72-hour period, you will be charged for the entire period of the reservation.

Airport Shuttle:  A Super Shuttle service is available for approximately $15 one way.

Taxi Service:  Approximately $30 one way.

Directions from Airport:  Take the 202 East, exit on Scottsdale Road. Go North 5 miles. Resort will be on the right, East side of Scottsdale Road between Vista and Jackrabbit.  If you rent a car, there is no charge to park at the hotel.

Directions From:

I-17 - Take Camelback East. Turn left or North, on Scottsdale Road for 1 mile. The Doubletree Paradise Valley Resort will be on the right, at the corner of Jackrabbit and Scottsdale Rd.

I-60 - Take Rural Road North. Rural Rd. will become Scottsdale Rd. When you go through the intersection of Camelback and Scottsdale Rd., the hotel will be on the right, just one more mile.

I-10 - Take HWY 143(Hohokam Expressway) north to 44th St. 44th St. will become McDonald. Turn right onto Scottsdale Rd for 1 mile. Turn left into the resort on Jackrabbit and Scottsdale Road.

# Hotel Information for the 2004 Meeting

Hilton Clearwater Beach

400 Mandalay Avenue

Clearwater, FL 33767
Tel: 1-727-461-3222

Fax: 1-727-461-0610

Rate: $125/night plus tax, single or double.   Cut-off for group rate: December 8, 2003, or when the room block is filled, whichever occurs first.

The Hilton Clearwater Beach is located overlooking the Gulf of Mexico.  The hotel sits on 10 lush acres along a beautiful white sandy beach. All guest rooms are spacious and are beautifully appointed room amenities include down pillows, complimentary morning newspaper, coffee maker with gourmet coffee and tea as well as up-to-the-minute technology such as dual line telephones with voice mail and high speed internet access.  The rooms have been newly renovated and most offer a water view.  The hotel also offers a pool and fitness facility and two restaurants.

Attractions close by include:  Show Queen Riverboat (walking distance), Clearwater Marine Aquarium (.5 miles), the Pro Beach Volleyball Hall of Fame (2 miles), and Orlando and Disney World (90 miles).

A one-night deposit is required and may be guaranteed with a credit card.  Individual cancellations must be received 48 hours prior to arrival or deposit is forfeited and credit card will be charged for one night’s accommodation.

There is an early departure fee if guest departs early.  Departure date will be re-confirmed upon check–in at which time the guest will be given the opportunity to adjust their date without penalty.

In making your hotel reservation, please identify yourself as an attendee of the Information Systems meeting. The code is ISSM.

# APPENDIX G

##### PARTICIPANT REGISTRATION FORM -2006

American Accounting Association 2006 Information System Section Midyear Conference January 6 – 7, 2006 and AIS New Scholars Consortium January 4 – 5, 2006 Scottsdale, Arizona Preliminary Program ¦ Conference Information ¦ Hotel Information New Scholars Consortium Registration Information Preregister Online* Registration Fee Registration fee includes registration for the meeting, Friday and Saturday continental breakfasts and lunches, and the Friday evening reception. Early registration deadline is December 5. Students Students registering for this meeting must be a current student member of the American Accounting Association to qualify for the student registration fee. Students should indicate on the registration form if they will attend the AIS New Scholars Consortium and/or the Mid-Year Meeting. Register Online *The AAA accepts only VISA or MasterCard. Mail Registration Make checks payable to the American Accounting Association. Mail registration forms to: American Accounting Association, 5717 Bessie Drive, Sarasota, FL 34233-2399 Cancellation Policy All cancellations must be received in writing at AAA (email Office@aaahq.org) in order to be processed. Cancellation requests received after December 16 will incur a $25 cancellation charge. No refunds will be available for cancellations after December 30, or for no-shows. Americans with Disabilities Act The American Accounting Association intends to comply fully with the Americans with Disabilities Act (ADA). Any members planning to attend this meeting who have special needs, as covered by the ADA, are requested to notify Debbie Gardner at the American Accounting Association, debbie@aaahq.org or (941) 556-4101 to facilitate identification and accommodation of these needs by the Association. Back to the Information Systems Section Home Page Back to AAA Home Page

APPENDIX H

LETTER TO REVIEWERS

(JIS Editor sends these)

July 7, 2006

Prof. «ReviewersName»

«Address_line_1»

«Address_line_2»

«ReviewersInstitution»

«City» «State»  «Zippostal_code»

«Country»

Dear «Greeting»:

I write to request your help in evaluating the publishability of the attached manuscript “ «Title»” (MS# «Manuscript»), which has been submitted for the «Typesection» section of the Journal of Information Systems (JIS).  I would like to receive your review by «Date_review_due».  If you will be unable to send your review by this date (or shortly thereafter), could please notify me via email as soon as possible?

Upon completion, please send your review as a Microsoft Word email attachment to both me (dstone@uky.edu) and the Associate Editor.  The Associate Editor on this manuscript is:

Prof «Associate_editorsName»

«Associate_editorsInstitution»

«Associate_editorsEmail_address»

Your review will serve two functions: (1) evaluating the appropriateness of the manuscript for JIS and (2) helping the author(s) improve the manuscript.  For your reference, I have attached a copy of the JIS editorial policy.  Please return (via email to dstone@uky.edu and the Associate Editor): (1) the attached review form, (2) any additional comments or recommendations for the editors, and (3) your review comments for the authors.  If you choose, please also mail a marked up copy of the manuscript pages with your comments to the Associate Editor.  In writing your review, please consider the following suggestions:

- Author(s) greatly appreciate prompt responses to their submissions.  In addition, prompt responses to submissions are critical to maintaining JIS as a quality publication outlet.  If delivering an early review is not possible, please make every effort to deliver a timely review.

- Please indicate whether the manuscript should be accepted, revised, or rejected in your correspondence with the Associate Editor, not in your letter to the author(s).

- If the paper is inappropriate for JIS, please include comments that will help the authors get the paper published elsewhere when possible.

Delivering quality reviews takes considerable time and effort.  I sincerely appreciate your valuable contributions of time and attention on behalf of JIS and academic accounting research.

Sincerely,

# Dan N. Stone

Editor

Email: dstone@uky.edu

Gatton Chair of Accounting Research

Univ. of Kentucky

School of Accountancy

355 Business & Economics

Lexington, KY 40506-0034

Phone: 859-257-3043

Fax: 859-257-3654

Attachments: JIS editorial policy, manuscript

APPENDIX I

REVIEWER EVALUATION FORM

Review Form: Journal of Information Systems

Type: 	Manuscript no.: «manuscript»

Title: «title»

Reviewer #: «reviewer»	Date due:

Associate Editor #: «AE»

1. Please indicate your recommendation regarding this manuscript:

_____	Accept for publication subject to minor changes indicated in memorandum and/or manuscript.

_____	Revise and resubmit.  The manuscript has the potential to contribute to the AIS literature, if the authors address review comments satisfactorily.

_____	Reject, with encouragement to resubmit.  The manuscript addresses an important topic but has serious flaws.  The manuscript may eventually be publishable but only after major revisions.  The revised manuscript would constitute a new submission.

_____	Reject, with no encouragement to resubmit.  The manuscript has significant irreparable flaws, or does not contribute to the AIS literature, and cannot be made publishable.

2. Either in the space provided below, or in a separate memorandum (which will not be sent to the author), please provide a candid assessment of this manuscript.

3. In a separate memorandum (which will be sent to the author), please assess the strengths and weaknesses of the paper.  Please address the following questions:

- Does the paper address a critical accounting, technology, or systems problem?

- How does the paper contribute to AIS knowledge?  How interesting and important is it to the JIS readership?

- What is the paper’s contribution to theory? What is the paper’s contribution to practice?  Does it effectively review prior literature?

- Are the research and data analysis methods appropriate?

- Are the conclusions supported by relevant evidence and arguments?

- Is the paper interesting, readable, and well written?

APPENDIX J

CONFERENCE REJECTION LETTER

(JIS Editor and Conference-Only Coordinator develop these)

July 7, 2006

Professor «Name»

«Address_line_1»

«Address_line_2»

«Institution»

«City», «State» «Zippostal_code» «Country»

Dear «Greeting»,

Thanks again for submitting your paper entitled, “«ManuscriptsTitle»” for publication in JIS and presentation at the AIS mid-year conference submissions process.  Unfortunately, I am rejecting your paper for presentation at the conference.

I’ve attached the comments and suggestions of two knowledgeable, experienced reviewers and the Associate Editor.  All recommend rejection of your paper.  There is substantial overlap in the recommendations of the reviewers and the Associate Editor, which I need not reiterate.  However, I offer the following suggestions:

I appreciate your interest in and support of the AAA-IS section research conference and the Journal of Information Systems.  I hope to see you in San Diego in January.

Sincerely,

Dan N. Stone

Editor – Journal of Information Systems

APPENDIX K

CONFERENCE ACCEPTANCE LETTER

November 12, 2001

Professor «Name»

«Address_line_1»

«Address_line_2»

«Institution»

«City», «State», «Zippostal_code» «Country»

Dear «Greeting»,

I am delighted to inform you that your co-authored paper entitled, “ «ManuscriptsTitle» ”has been tentatively accepted for presentation at the first annual AIS Research Symposium.  Acceptance of your paper for the AIS Research Symposium is an impressive accomplishment; only -- of the twenty-one submitted papers ( ) were accepted for presentation at the conference.

Your conference presentation will be on either Friday, January 10 or Saturday, January 11 at a time to be determined.  Discussants and moderators for the conference have not yet been chosen.  More information about the conference is available at: http://aaa-is.byu.edu/.  Conference papers will be available to participants at the soon-to-be-developed conference website (http://aaa-is.byu.edu/jis/midyear/).

Ultimate acceptance of your paper for presentation at the conference depends upon your timely completion of the following:

- by November 15, 2002, please notify me of your commitment to attend the conference and present your paper (by email to dstone@uky.edu)

- Please edit and revise the submitted manuscript based upon the attached comments, as you deem appropriate.

- by December 10, 2002, please send an email message with your completed manuscript (including all tables, figures, and references) to Professor Jack Cathey (jmcathey@email.uncc.edu), me (dstone@uky.edu), and the discussant (still to be assigned).  Your paper must be in either Adobe Acrobat pdf or Microsoft Word format.

Please email or call me if you have questions regarding the paper.

I look forward to seeing you at the meeting.

Sincerely,

Dan N. Stone

Editor – Journal of Information Systems

APPENDIX L

FORUM ACCEPTANCE LETTER

July 7, 2006

Professor «Name»

«Address_line_1»

«Address_line_2»

«Institution»

«City», «State» «Zippostal_code» «Country»

Dear «Greeting»,

I am pleased to inform you that I am accepting your paper entitled “ «ManuscriptsTitle» ” for the paper forum session at the AIS Teaching & Research Symposium.  This session provides the opportunity for conference attendees to individually discuss your paper with you.  The forum session will be held on Saturday morning, January 11, at the Holiday Inn Mission Bay, San Diego, California.

Final acceptance of your paper for the paper forum session depends upon your timely completion of the following:

- Please notify me of your commitment to attend the conference and forum by December 2, 2002 (by email to dstone@uky.edu)

- Please edit and revise the document based upon the attached comments, as you deem appropriate.

- No later than December 16, please send an email message with your completed manuscript (including all tables, figures, and references) to me.  Your paper must be in either Adobe Acrobat pdf (preferred) or Microsoft Word (discouraged) format.

Please bring at least 15 copies of the paper with you to share with interested conference attendees.

I look forward to seeing you at the meeting!

Sincerely,

Dan N. Stone

Dan N. Stone

Editor – Journal of Information Systems

APPENDIX M

Author and Discussant Guidelines

(New Format in 2005, Continued New Format in 2006)

Guidelines posted on the Section website and in the Program.

Format for Paper Sessions

(all sessions are 90 minutes)

We will use the same format this year that we used last year in New Orleans.  Our hope is that this format will provide authors valuable feedback to improve their research. Also, this format should encourage audience participation and discussion, which fosters a more collegial atmosphere.

Thank you - we sincerely hope you enjoy the 2006 Midyear Meeting!

Research Papers*

2 papers/session – 45 minutes/paper: 20 discussant, 10 author, 15 audience

* The discussant’s primary role is to summarize the paper, rather than critique it.  The discussant’s 
   suggestions for improving the paper would best come as part of the audience participation.

Educational/Instructional Papers

2 papers/session – 45 minutes/paper: 25 author, 20 audience

3 papers/session – 30 minutes/paper: 20 author, 10 audience

Author and Discussant Guidelines – Used in 2004 and Prior Years

2004 AAA-IS Midyear Meeting

January 7-10, 2004

Clearwater, Florida

Starting the Session

The moderator’s job is to start the session on time and keep the authors and discussants within their allotted time.  Please be in the appropriate room a few minutes early so the moderator will be able to start the session on time.

Technology Considerations

Authors and discussants are responsible for having their presentations loaded on the computer and ready to go prior to the session.  To this end, authors and discussants should email your presentations to the conference chair (Stephanie Bryant, sbryant@coba.usf.edu) at least 24 hours prior to the conference.  If there are any problems with the technology during the presentation, the moderator will contact the AAA staff who will be on site to facilitate the meeting.

We strongly recommend authors and discussants have a contingency plan in case of technology failure.  Overhead transparencies are usually the best backup plan.

Conducting the Session

Your session will have either two or three papers and will be either an hour and a half or two hours long.  The papers will be presented sequentially according to the order in the program, followed by a single discussant who will discuss each paper. The moderator will introduce all authors and papers at one time, and announce how long each author has to present the paper and how long the discussant will have for discussion of all the papers.  The moderator will cue the presenter when 5 minutes are remaining, and again when time is up.

It is important to keep the session on track time-wise.  Check to see how long your session is and how many papers will be presented.  You will have one of the following blocks of time:

| Length of session | Number of papers | Allow for each paper presentation | Allow for discussant |
| --- | --- | --- | --- |
| 1-1/2 hours | 2 | 30 min | 30 min |
| 1-1/2 hours | 3 | 20 min | 30 min |
| 2 hours | 2 | 40 min | 40 min |
| 2 hours | 3 | 30 min | 30 min |

The most challenging block is 3 papers in an hour and a half.  Please be respectful of the people are following you!  Watch your time and when the moderator cues you with the 5 minute warning, begin wrapping it up.  When the moderator cues you that time is up, wrap it up within 30 seconds.

If time allows (only after the discussant is finished), certainly take questions from the audience.

What to Present—Authors

Because several papers will be presented sequentially, begin by introducing yourself and any co-authors present.  If you have handouts, it’s best to hand them out at the beginning of your presentation.  Your moderator can help you do this.  It is not necessary to bring copies of your paper with you to distribute, though some authors choose to do so.

The conference papers are available for download on the Web (see

http://aaa-is.byu.edu/Events/2004Midyearpapers/default.htm).  Thus, you can assume people have read your paper.   Don’t spend a great deal of time on literature review.  Go with the main points.  If you are running short of time, know which slides your most important results are on so you can skip ahead if necessary.   Try to limit the number of slides to no more than 10-15.  It will help you manage your time and focus your discussion.  End with a strong summary, and thank the audience for their attention.

The Discussant’s Role

After all papers for the session have been presented, the discussant will then discuss the papers, in the order they were presented.  The discussant has discretion as to how much time he/she spends on each paper.  For the papers that have been accepted for publication in JIS, it is expected that the discussant will spend more time on these papers.

The discussant’s job is to tell what he/she liked about the paper and how the paper might be improved.  The discussant usually has a PowerPoint presentation which covers his/her main points.  The discussant should also provide the authors with a written copy of his/her comments.

# Author’s Response to Discussant Comments

If time allows,  the author may wish to respond to the discussant’s comments.  This is at the author’s discretion.  The author should let the moderator know if he/she wishes to respond to the discussant’s comments.  Remember though, in some sessions, time may not allow for extensive response.  Be considerate of those that will follow and stay within the total time allowed for your paper.

Questions?

If you have any questions, please contact the conference chair, Stephanie Bryant (sbryant@coba.usf.edu).

APPENDIX N

Moderator Guidelines for 2006

Thank you for agreeing to serve as a moderator for the AAA-IS Section Midyear Meeting.  Your role in the meeting is very important in that you ensure a session runs in an orderly, efficient manner and within the allotted time.  Below are some guidelines to assist you.

Starting the Session

As moderator, you will ensure that the session starts on time.  Sometimes this takes a little prompting at the microphone to get people seated and ready for the session to begin.  You can begin announcing the start of the session a couple of minutes prior to the scheduled start time, if needed.  Begin the introductions at the scheduled time.

Technology Considerations

The author is responsible for having his/her presentation loaded and ready to go prior to the session.  However, it’s a good idea to touch base with the authors and discussant ahead of time in case they’ve neglected to do this.  If there are any problems with the technology during the presentation, contact the AAA staff who will be on site to facilitate the meeting.

Conducting the Session

Your session will have either two or three papers and your session will be 90 minutes long. The amount of time should be equally distributed between the papers.  Please introduce all authors and papers at the beginning of the session.  If the papers are education papers, announce how long each author has to present the paper and entertain questions.  If the papers are considered research papers, then each paper will have a discussant who will present (summarize) the paper and then the author (s) about 5 minutes to respond, followed by questions from the audience.  Remind the presenters/discussants that you will cue them when they have 5 minutes remaining, and again when their time is up. The authors (education papers) or the discussants (research papers) will then present the papers sequentially, according to the order printed in the program.

It is important to keep the session on track time-wise.  Check the program to see how long your session is and how many papers will be presented.  You will have one of the following blocks of time:

| Length of Session | Number of papers | Total Time per Paper | Research Papers, Discussant has | Research Papers, Author has | Education Papers, Author has |
| --- | --- | --- | --- | --- | --- |
| 90 min. | 2 | 45 min. | 15 min. | 10 min. | 45 min |
| 90 min. | 3 | 30 min. | 12 min. | 7 min. | 30 min |

The most challenging block is 3 papers in an hour and a half.  You will have to be vigilant here to keep the session on track.  It’s a good idea to sit where you can discreetly cue the presenter or discussant when time is running short.

If time allows (only after the discussant is finished), certainly take questions from the audience.

Wrapping Up

After the discussant has finished, please thank all of the authors and the discussant and lead the applause.

Questions?

If you have any questions, please contact Mary Curtis:  curtism@unt.edu

Moderator Guidelines – Used in 2004 and Prior Years

2004 AAA-IS Midyear Meeting

January 7-10, 2004

Clearwater, Florida

Thank you for agreeing to serve as a moderator for the AAA-IS Section Midyear Meeting.  Your role in the meeting is very important in that you ensure a session runs in an orderly, efficient manner and within the allotted time.  Below are some guidelines to assist you.

Starting the Session

As moderator, you will ensure that the session starts on time.  Sometimes this takes a little prompting at the microphone to get people seated and ready for the session to begin.  You can begin announcing the start of the session a couple of minutes prior to the scheduled start time, if needed.  Begin the introductions at the scheduled time.

Technology Considerations

The author is responsible for having his/her presentation loaded and ready to go prior to the session.  However, it’s a good idea to touch base with the authors and discussant ahead of time in case they’ve neglected to do this.  If there are any problems with the technology during the presentation, contact the AAA staff who will be on site to facilitate the meeting.

Conducting the Session

Your session will have either two or three papers.  Tell the audience that the papers will be presented sequentially, followed by a single discussant who will discuss each paper. Please introduce all authors and papers at one time.  Announce how long each author has to present the paper and how long the discussant will have for discussion of all the papers.  Remind the presenters and discussant that you will cue them when they have 5 minutes remaining, and again when their time is up. The authors will then present the papers sequentially, according to the order printed in the program.

It is important to keep the session on track time-wise.  Check the program to see how long your session is and how many papers will be presented.  You will have one of the following blocks of time:

| Length of session | Number of papers | Allow for each paper presentation | Allow for discussant |
| --- | --- | --- | --- |
| 1-1/2 hours | 2 | 30 min | 30 min |
| 1-1/2 hours | 3 | 20 min | 30 min |
| 2 hours | 2 | 40 min | 40 min |
| 2 hours | 3 | 30 min | 30 min |

The most challenging block is 3 papers in an hour and a half.  You will have to be vigilant here to keep the session on track.  It’s a good idea to sit where you can discreetly cue the presenter or discussant when time is running short.

If time allows (only after the discussant is finished), certainly take questions from the audience.

Wrapping Up

After the discussant has finished, please thank all of the authors and the discussant and lead the applause.

Questions?

If you have any questions, please contact the conference chair, Stephanie Bryant (sbryant@coba.usf.edu).

APPENDIX O

VOLUNTEER FORM

(Obsolete – Online ONLY)

Starting in 2006, the volunteer form for the Midyear Meeting was located on the IS Section website. This form was developed by Section members and enabled by Kathy Casper at the AAA. While this online option is useful for the Midyear Meeting, the 2006 Program Chair is working with the AAA to develop a permanent online volunteer option that may be used for a variety of responsibilities throughout the year.  Kathy Casper will develop a database for our Section that will allow us to collect volunteer information and save the information in a spreadsheet for various uses.  A generic form is being developed.

This volunteer option is SEPARATE from the Annual Meeting information that is collected BY the AAA and used exclusively for the purposes of the Annual Meeting.

APPENDIX P

##### FINAL REPORT TO THE SECTION

MEMORANDUM

To:	AAA-IS Executive Committee

From:	Carolyn Strand Norman, 2006 AAA-IS Midyear Meeting Chair

Date:	January 2, 2006

Re:	Report to the Executive Committee on 2006 IS Midyear meeting

# Overview

The 5th annual AAA-IS midyear meeting was held January 4-7th 2006 at the Doubletree Paradise Valley Resort in Scottsdale, Arizona. The meeting was preceded by the New Scholar Consortium chaired by Uday Murthy, JIS Research Workshop chaired by Tanya Lee, and SMAP organized by Julie Smith David. The Consortium was on January 5th and the IS Section Conference was on the 6th and 7th and included a plenary session, 9 concurrent sessions, and a research forum session. The final session was “Research Topics” panel discussion. We again used the format for research paper sessions that was used last year – that is, discussants summarized papers to encourage more audience participation. The discussants were again reminded of their responsibilities under this format. Also, the guidelines were printed in the Meeting Program. No discussants were used in the education paper sessions.

# Final Registration Numbers (a/o 1-3-06):

New Scholars Consortium		30

Doctoral Students	  	12

1st /2nd  Yr AIS Profs	18

SMAP					24

Midyear Meeting

Preregistered     		             119

On-site

Doctoral Students	  13

IS Members		111

Non-IS Members 	    8

Guests			  14

# Meeting Costs

In an effort to break even on this year’s meeting, we did the following:

- The registration fee was increased to $225 and SMAP registration was increased to $120.

- Scott’s suggestion to have Section members bring laptops/projectors for the presentations in the paper sessions saved several thousand dollars this year. Scott Summers, Julie Smith-David and Mary Curtis brought equipment for the paper sessions and for SMAP. Mary Curtis purchased Kensington locks to protect the equipment.

- We have a water station rather than bottled water ($4.25 a bottle).

- We also changed the receptions to “light snacks” and included this information in the Program that was posted on our Section website (before the Meeting) to alert our members that this would be a time to meet with colleagues and make dinner plans. In addition, the receptions are all “cash bar” this year.

- The food costs are summarized in the attached spreadsheet, which includes most of the costs. We did not know the cost of coffee and tea for the morning and afternoon breaks, so this is not included in the spreadsheet. However, gratuity (20%) and tax (7.95%) are included. The total estimated food costs are $19,935.

- The cost of this year’s meeting is compared with prior meetings:

|  | 2006 Estimated | 2005 Actual | 2004 Actual | 2003 Actual | 2002 Actual |
| --- | --- | --- | --- | --- | --- |
| Location: | Scottsdale | New Orleans | Clearwater | San Diego | Orlando |
| Attendance*: | 130 | 135 | 124 |  | 129 |
| Revenue: | $29,400.00 | $ 30,655.00 | $ 28,310.00 | $ 20,950.00 | $ 22,075.00 |
| Expenses: | 28,528.25 | 33,649.69 | 22,419.85 | 27,902.94 | 30,683.26 |
| Net: | $ 874.75 | $ (2,994.69) | $ 5,890.15 | $ ( 6,952.92) | $ (8,608.26) |

*Includes IS Members, non-members, PhD students, and guests.

KPMG contributed $5,000 to support the New Faculty Consortium.

# Summary of Papers

Number of papers in regular sessions			16

AI/ET has 2 sessions (1 is a panel discussion)	  2

Number of papers in forum session			17

Total number of papers on program 			35

# Paper Awards

Research Award:  “Policy-Level Specification in REA Enterprise Information Systems,”  Authors: Guido Geerts (University of Delaware), William E. McCarthy (Michigan State University)

Education Award: “The United States Department of the Treasury Bureau of Engraving and Printing Tests an E-Procurement System,”  Authors: Ulric Gelinas and Janis L. Gogan (Bentley College)

# Notes for this Meeting

To enhance Scott’s idea of Section members bringing A/V equipment, we should consider finding a Technology Manager, that is, a full-time volunteer (perhaps a 3-year commitment) who would be responsible for finding individuals to bring equipment. At the Meeting, the Technology Manager would be responsible for helping presenters load their PP presentations on the laptops and assisting if there are any equipment problems. As with this year, we should have 3 sets of equipment (laptop/projector) – two for the concurrent paper sessions and one set as a back-up. Mary Curtis purchased Kensington locks for this year and these would be turned over to the Technology Manager. Stephanie suggested that we should consider offering the Technology Manager free registration for the Meetings in exchange for this service.

We only have KPMG funding for the 2005, 2006, and 2007 Meetings.  We should probably consider additional sources of funding, and perhaps seek a higher commitment from KPMG for future meetings.

Memorandum

To:	AAA-IS Section Executive Committee

From:	Stephanie Bryant, 2004 AAA-IS Midyear Meeting Program Chair

Date:	January 10, 2004

Re:	Report to the Executive Committee on 2004 IS Midyear Meeting

# Overview

The third annual AAA-Information Systems meeting was held January 7-10, 2004 at the Hilton Clearwater Beach Resort in Clearwater, Florida.  The meeting was preceded by a New Scholar Consortium, to which AIS doctoral students and 1st and 2nd year assistant professors were invited.  SMAP was also run as a CPE session and was very well received.  Additionally, the AAA-AI/ET section sponsored some concurrent sessions.  A copy of the final program accompanies this memo via email.  Special guests included Dr. Jane Mutchler, president-elect of AAA, who was the plenary session speaker; and Eddie Munson, KPMG National Partner in Charge of Recruiting.

# Final Registration Numbers for 2004 IS Midyear Meeting

Doctoral students		 		  	  19

IS Members						102

Non-IS member attendees	   		   	   1

Guests							   2

Total attendees					            124

Other information included in above numbers:

1st and 2nd year assistant professors		 	14                                                                                                attending New Scholar Consortium

Total participants for New Scholar Consortium                                                                                                                                                  (excluding leaders)                                                      	34

SMAP participants (excluding leaders)		 	26

# Meeting Costs

Clearwater proved to be an inexpensive city for hosting the meeting.  We budgeted for essentially a breakeven meeting.  In the end, food and hotel costs were significantly less than projected.  The Show Queen River Boat dinner and cruise Friday night cost $2,940 (roughly $23 per person), significantly less than we usually spend for the Friday evening reception.  The cash bar also helped keep costs down.  The Executive Committee should be aware that future meetings such as the 2005 meeting in New Orleans will undoubtedly be a more expensive location.

|  | 2004 Budget | 2004 Actual | 2003 Actual |
| --- | --- | --- | --- |
| Revenue | $26,300.00 | $28,310.00* | $20,950.00 |
| Expenses | 26,351.00 | 22,419.85 | 27,902.94 |
| Net | $( 51.00) | $ 5,890.15 | $( 6,952.92) |

*Actual revenue of $28,310 includes $5,000 contribution from KPMG that has been invoiced but not yet received.

# Summary of Papers

Number of papers on program			22                                                                        (16 IS papers, 6 AI/ET papers)

Number of papers in forum			10

Total number of papers on the program		32

# Paper Awards

Outstanding Academic Paper Award:  Eileen Taylor for “The Effect of Incentives on Knowledge Sharing in Computer-Mediated Communication:  An Experimental Investigation”

Outstanding Education Paper Award:  A tie between David Hayes for “Caroline’s Candy Shop:  An In-Class Illustration of the Revenue Cycle” and Faye Borthick for “Analyzing a Potential Warranty Call Center Budget Overrun:  Using Database Queries to Solve Business Problems.

# Future Funding from KPMG

The KPMG Foundation has agreed to fund our doctoral consortium (New Scholars’ Consortium) for three years at $5,000 per year, starting January of 2005.

##### APPENDIX Q

BUDGET

(THIS IS AN EXCEL FILE)

APPENDIX R

PAST MEETING PROGRAMS

In Archive on IS Section website.

APPENDIX S

CONFERENCE EVALUATION FORM

Please rate each of the following aspects of our Meeting:

Poor              Below                 OK                Very          Excellent					         	   	      Average	                             Good

| Hotel Accommodations | 1 | 2 | 3 | 4 | 5 | NA |
| --- | --- | --- | --- | --- | --- | --- |
| Meeting Site – Scottsdale, AZ | 1 | 2 | 3 | 4 | 5 | NA |
| Breakfasts | 1 | 2 | 3 | 4 | 5 | NA |
| Breaks | 1 | 2 | 3 | 4 | 5 | NA |
| Lunches | 1 | 2 | 3 | 4 | 5 | NA |
| Receptions | 1 | 2 | 3 | 4 | 5 | NA |
| Registration | 1 | 2 | 3 | 4 | 5 | NA |
| New Scholar Consortium | 1 | 2 | 3 | 4 | 5 | NA |
| JIS Research Workshop | 1 | 2 | 3 | 4 | 5 | NA |
| Semantic Modeling of Accounting Phenomena (SMAP) | 1 | 2 | 3 | 4 | 5 | NA |
| Plenary Session | 1 | 2 | 3 | 4 | 5 | NA |
| Research Forum – Saturday afternoon | 1 | 2 | 3 | 4 | 5 | NA |
| Format for Research Sessions | 1 | 2 | 3 | 4 | 5 | NA |
| Education Sessions | 1 | 2 | 3 | 4 | 5 | NA |

1.  What did you like best about the AAA-IS section meeting this year?

2.  Do you have any specific suggestions for improving the AAA-IS Section Midyear Meeting 
     for next year in Savannah, GA?

3.  Would you be in favor of a joint meeting with any of the following sections for our 2008 Midyear Meeting?    
      Please indicate a “1” for your first choice; and a “2” for your second choice.

_____ Auditing    	   _____ Management Accounting	 	 _____ ABO	      _____ AI/ET